## Drilling Budget Drft1 Detailed (hidden)
Polymetals Australia Pty Ltd -- Woodcutters Project
WOODCUTTERS DRILLING BUDGET PROGRAMME 2000
PROSPECT | EXPENDITURE | Drilling |  | File: | MST-DRBUD
|  |  |  | Date: | 2026-07-30 09:05
WC L5 & L1 | PROJECT NAME | Woodcutters
COST ACTIVITY
Administration General | Cost per Day | Total days | Cost/kg | Total/kg | Cost | Cost/m
Travel * |  |  |  |  | 4000
Accomodation and Meals | 100 | 30 |  |  | 3000
Freight * |  |  | 1.8 | 100 | 180
Vehicle | 120 | 30 |  |  | 3600
Sub Total |  |  |  |  | 10780 | 3.8847
Analytical General | Cost/sample | Total Number
Assaying | Estimate | Samples
Fire Assay 30 Au | 5.5 | 500 |  |  | 2750
G340I Pb, Zn, Ag, As,Sb,Cd | 8 | 2775 |  |  | 22200
Sample Prep | 2.5 | 2775 |  |  | 6937.5
G300I | 6.5 | 0
Sample Pickup | 0.25 | 2775 |  |  | 693.75
Sub Total |  |  |  |  | 32581.25 | 11.741
Drilling General | Cost/hr $AUD | Total Hours | Drilling Cost/m $AUD | Total Metres
| Rig moves etc | Budgeted | Budgeted
Aircore |  |  | 15 | 225 | 3375
RC |  |  | 28 | 2775 | 77700
Diamond |  |  | 80
Mobilisation * |  |  |  |  | 0
Demobilisation * |  |  |  |  | 0
Standby | 206 | 10.3 |  |  | 2121.8
Collaring | 275 | 46 |  |  | 12650
Shifting | 275 | 11.5 |  |  | 3162.5
Reaming | 275 | 6.9 |  |  | 1897.5
Clearing Rods | 275 | 2.3 |  |  | 632.5
Consumables
PVC m |  |  | 21.5 | 480 | 10320
Foamit kg |  |  | 9.62 | 45 | 432.9
Drill Foam l |  |  | 20 | 10 | 200
Budgeted Total Hrs |  | 230
Sub Total |  |  |  |  | 112492.2 | 40.5377
Geology General |  |  | Cost/unit | Total Number
|  |  | Estimate | Units
Geol Consumables
Sample Bags 1m Plastics |  |  | 0.56 | 2775 | 1554
Calico Sample Bags |  |  | 0.38 | 2775 | 1054.5
Sample Bags 1m Calicos |  |  | 1.27 | 2775 | 3524.25
Drill Chips |  |  | 2 | 140 | 280
Survey Pegs |  |  | 0.9 | 250 | 225
Sample Books |  |  | 3.7 | 30 | 111
Flagging Tape |  |  | 3.7 | 25 | 92.5
Bucket |  |  | 9.6 | 5 | 48
Seive |  |  | 5.25 | 8 | 42
Poly Chain |  |  | 172 | 0 | 0
Earplugs |  |  | 0.6 | 50 | 30
Water Cooler |  |  | 19.15 | 0 | 0
Acid Dropper |  |  | 1 | 5 | 5
Contactor General
Sub Total |  |  |  |  | 6966.25 | 2.5104
Managemnent | Cost/day | Total Days
Supervision | 300 | 30 |  |  | 9000
Gridding | 300 | 30 |  |  | 9000
Sub Total |  |  |  |  | 18000 | 6.4865
Site General
Site Rehabilitation | 300 | 5 |  |  | 1500
Site Preperation | 800 | 5 |  |  | 4000
Geotechnical |  |  |  |  | 0
Hydrology |  |  |  |  | 0
Metallurgy | 500 | 7 |  |  | 3500
Archaeology (Native Title) | 500 | 2 |  |  | 1000
Subtotal |  |  |  |  | 10000 | 3.6036
Programme Subtotal |  |  |  |  | 190819.7 | 68.7639
Note * Equtaes to fixed Cost

## Moline Tailings DamProg. Budget
PMA Moline Tailings Dam Drilling Budget 2000
PROSPECT | EXPENDITURE | Drilling | File: | MST-DRBUD
Tailings Dam | PROJECT NAME | Moline
COST ACTIVITY
Administration General | Cost per Day | Total days | Cost/kg | Total/kg | Cost | Cost/m
Travel * |  |  |  |  | 1557.6
Accommodation and Meals
1 Field Crew Option | 120 | 6 |  |  | 720
Freight * |  |  | 1.8 | 10 | 18
Data Logger Hire | 50 | 0 |  |  | 0
Vehicle | 70 | 6 |  |  | 420
Sub Total |  |  |  |  | 2715.6 | 13.578
Assaycorp
Analytical General | Cost/sample | Total Number |  |  | Total
Assaying | Estimate | Samples |  |  | Cost
Fire Assay 30 Au | 5.5 | 0 |  |  | 0
G340I Pb, Zn, Ag, As,Sb,Cd | 8 | 40 |  |  | 320
Sample Prep | 3.5 | 40 |  |  | 140
G300I | 6.5 | 0 |  |  | 0
Duplicates Total Cost | 11.55 | 0 |  |  | 0
Sample Pickup | 0.25 | 0 |  |  | 0
Sub Total |  |  |  |  | 460 | 11.5
Wallis
Drilling General | Cost/hr $AUD | Total Hours | Drilling Cost/m | Total Metres | Total
| Rig moves etc | Budgeted | Budgeted |  | Cost
Aircore |  |  | 14 | 200 | 2800
RC |  |  | 26 | 0 | 0
Diamond |  |  | 80 | 0 | 0
Mobilisation * |  |  |  |  | 0
Demobilisation * |  |  |  |  | 0
Standby | 140 | 1 |  |  | 140
Collaring | 290 | 0 |  |  | 0
Shifting | 290 | 2 |  |  | 580
Reaming | 290 | 0 |  |  | 0
Clearing Rods | 290 | 0 |  |  | 0
Changing Drill Type | 290 | 0.5 |  |  | 145
Consumables
PVC m |  |  | 21.5 | 0 | 0
Foamit kg |  |  | 9.62 | 0 | 0
Drill Foam l |  |  | 20 | 0 | 0
Budgeted Total Hrs |  | 3.5
Sub Total |  |  |  |  | 3665 | 18.325
Geology General |  |  | Cost/unit | Total Number | Total
|  |  | Estimate | Units | Cost
Geol Consumables
Sample Bags 1m Plastics |  |  | 0.51 | 200 | 102
Calico Sample Bags |  |  | 0.35 | 200 | 70
Sample Bags 1m Calicos |  |  | 0.8 | 0 | 0
Drill Chips |  |  | 1.5 | 0 | 0
Survey Pegs |  |  | 0.9 | 50 | 45
Sample Books |  |  | 3.8 | 0 | 0
Flagging Tape |  |  | 3 | 2 | 6
Bucket |  |  | 8.3 | 5 | 41.5
Sieve |  |  | 10 | 0 | 0
Poly Chain |  |  | 172 | 0 | 0
Earplugs |  |  | 0.22 | 0 | 0
Water Cooler |  |  | 19.15 | 0 | 0
Acid Dropper |  |  | 0.9 | 5 | 4.5
Safety Dust Mask |  |  | 5 | 5 | 25
Marker Pens |  |  | 1.8 | 10 | 18
Polyweave Bags |  |  | 0.75 | 10 | 7.5
Sub Total |  |  |  |  | 319.5 | 1.5975
Management | Cost/day | Total Days |  |  | Total Cost
Supervision | 500 | 6 |  |  | 3000
Field Technician | 250 | 3 |  |  | 750
Sub Total |  |  |  |  | 3750 | 18.75
Site General |  | Total Days |  |  | Total Cost
Site Rehabilitation | 500 | 0 |  |  | 0
Site Preparation | 800 | 0 |  |  | 0
Geotechnical |  |  |  |  | 0
Survey | 1500 | 0 |  |  | 0
Hydrology |  |  |  |  | 0
Metallurgy | 1000 | 0 |  |  | 0
Archaeology (Native Title) | 500 | 0 |  |  | 0
Subtotal |  |  |  |  | 0 | 0
Programme Subtotal |  |  |  |  | 10910.1 | 54.5505
Contingency 10% |  |  |  |  | 1091.01
Total |  |  |  |  | 12001.11 | 60.0055
Note * Equates to fixed Cost

## WC PMA Prop.A Drilling 2000 (hidden)
Project | Woodcutters Proposed Drilling Programme February 2000
Date | 2000-02-29
Approved | PMA | Geologist |  | Client
Prospect No. | L5S
Area | North from Open Pit to L5 Core Shed Gossan
Planned | Planned | Target | Priority | Easting | Northing | Az | Dip | Comments
Hole No. | Depth m | Depth m
L5 STH
WCPMA1 | 50 |  | 1 | 5130 | 5200 | 90 | -65 | L5 South between open pit and L5
WCPMA1 | 60 |  | 1 | 5190 | 5300 | 90 | -60 | L5 South between open pit and L5
WCPMA2 | 65 |  | 1 | 5140 | 5320 | 90 | -60 | L5 South between open pit and L5
WCPMA3 | 50 |  | 1 | 5160 | 5340 | 90 | -60 | L5 South between open pit and L5
WCPMA4 | 50 |  | 1 | 5120 | 5360 | 90 | -60 | L5 South between open pit and L5
WCPMA5 | 50 |  | 1 | 5180 | 5360 | 90 | -60 | L5 South between open pit and L5
WCPMA6 | 40 |  | 2 | 5100 | 5360 | 90 | -60 | L5 South between open pit and L5
WCPMA7 | 40 |  | 1 | 5180 | 5380 | 90 | -60 | L5 South between open pit and L5
WCPMA8 | 50 |  | 1 | 5110 | 5380 | 90 | -60 | L5 South between open pit and L5
WCPMA9 | 50 |  | 2 | 5120 | 5400 | 90 | -60 | L5 South between open pit and L5
WCPMA10 | 50 |  | 1 | 5180 | 5400 | 90 | -60 | L5 South between open pit and L5
WCPMA11 | 50 |  | 1 | 5180 | 5420 | 90 | -60 | L5 South between open pit and L5
WCPMA12 | 45 |  | 1 | 5180 | 5440 | 90 | -60 | L5 South between open pit and L5 below Geochem anomaly
WCPMA13 | 60 |  | 1 | 5130 | 5440 | 90 | -60 | L5 South between open pit and L5 below Geochem anomaly
WCPMA14 | 50 |  | 1 | 5120 | 5460 | 90 | -60 | L5 South between open pit and L5 below Geochem anomaly
WCPMA15 | 50 |  | 1 | 5170 | 5460 | 90 | -60 | L5 South between open pit and L5
WCPMA16 | 50 |  | 1 | 5180 | 5480 | 90 | -60 | L5 South between open pit and L5
WCPMA17 | 40 |  | 2 | 5180 | 5500 | 90 | -60 | L5 South between open pit and L5
WCPMA18 | 50 |  | 1 | 5110 | 5500 | 90 | -60 | L5 South between open pit and L5
WCPMA19 | 50 |  | 1 | 5160 | 5520 | 90 | -60 | L5 South between open pit and L5
WCPMA20 | 40 |  | 1 | 5180 | 5520 | 90 | -60 | L5 South between open pit and L5
WCPMA21 | 50 |  | 2 | 5170 | 5540 | 90 | -60 | L5 South between open pit and L5
WCPMA22 | 50 |  | 2 | 5180 | 5560 | 90 | -60 | L5 South between open pit and L5
WCPMA23 | 65 |  | 1 | 5160 | 5560 | 90 | -60 | L5 South between open pit and L5
L5
WCPMA24 | 60 |  | 1 | 5160 | 5580 | 90 | -60 | Twin of original PMA hole
WCPMA25 | 80 |  | 1 | 5150 | 5580 | 90 | -70 | Below PMA Drilling at L5
WCPMA26 | 110 |  | 1 | 5140 | 5600 | 90 | -65 | Depth extension of drilling to test primary Zn mineralisation
WCPMA27 | 50 |  | 1 | 5210 | 5600 | 0 | -90 | Vertical hole testing potential supergene blanket
WCPMA28 | 95 |  | 1 | 5140 | 5620 | 90 | -65 | Depth extension of drilling to test primary Zn mineralisation
WCPMA29 | 110 |  | 1 | 5140 | 5640 | 90 | -65 | Depth extension of drilling to test primary Zn mineralisation
WCPMA30 | 75 |  | 1 | 5162 | 5640 | 90 | -60 | Depth extension of drilling to test primary Zn mineralisation
WCPMA31 | 65 |  | 2 | 5160 | 5660 | 90 | -60 | Depth extension of drilling to test primary Zn mineralisation
L1
WCPMA31 | 70 |  | 1 | 5080 | 8100 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA32 | 70 |  | 1 | 5080 | 8150 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA33 | 110 |  | 2 | 5060 | 8150 | 90 | -60 | Testing L1 primary Zn mineralisation
WCPMA34 | 30 |  | 1 | 5100 | 8200 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA35 | 60 |  | 1 | 5080 | 8200 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA36 | 65 |  | 1 | 5080 | 8250 | 90 | -60 | Twin hole from previous PMA drilling
WCPMA37 | 115 |  | 1 | 5060 | 8250 | 90 | -60 | Drilling below PMA previous intersection
WCPMA38 | 120 |  | 2 | 5040 | 8300 | 90 | -60 | Testing L1 primary Zn mineralisation
WCPMA39 | 60 |  | 1 | 5060 | 8300 | 90 | -60 | Twin hole from previous PMA drilling
WCPMA40 | 95 |  | 3 | 5180 | 8300 | 270 | -60 | Testing L1 primary Zn mineralisation
WCPMA41 | 60 |  | 1 | 5070 | 8350 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA42 | 60 |  | 1 | 5020 | 8400 | 90 | -60 | Testing L1 Geochem anomaly
WCPMA43 | 60 |  | 1 | 5050 | 8450 | 90 | -60 | Testing L1 Geochem anomaly
2825

## MolineTD Actual Costs
PMA Moline Tailings Dam September2000 Drilling Actual Costs
PROSPECT | EXPENDITURE | Drilling | File: | MST-DRBUD
Tailings Dam | PROJECT NAME | Moline
COST ACTIVITY
Administration General | Cost per Day | Total days | Cost/kg | Total/kg | Cost | Cost/m
Travel * |  |  |  |  | 1557.6
Accommodation and Meals
1 Field Crew Option | 120 | 6 |  |  | 720
Freight * |  |  | 1.8 | 0 | 0
Data Logger Hire | 50 | 0 |  |  | 0
Vehicle | 70 | 7 |  |  | 490
Sub Total |  |  |  |  | 2767.6 | 13.838
Assaycorp
Analytical General | Cost/sample | Total Number |  |  | Total
Assaying | Estimate | Samples |  |  | Cost
Fire Assay 30 Au | 5.5 | 0 |  |  | 0
G340I Pb, Zn, Ag, As,Sb,Cd | 8 | 33 |  |  | 264
Sample Prep | 3.5 | 33 |  |  | 115.5
G300I | 6.5 | 0 |  |  | 0
Duplicates Total Cost | 11.55 | 0 |  |  | 0
Sample Pickup | 0.25 | 0 |  |  | 0
Sub Total |  |  |  |  | 379.5 | 11.5
Wallis
Drilling General | Cost/hr $AUD | Total Hours | Drilling Cost/m | Total Metres | Total
| Rig moves etc | Budgeted | Budgeted |  | Cost
Aircore |  |  | 14 | 200 | 2800
RC |  |  | 26 | 0 | 0
Diamond |  |  | 80 | 0 | 0
Mobilisation * |  |  |  |  | 0
Demobilisation * |  |  |  |  | 0
Standby | 140 | 0 |  |  | 0
Collaring | 290 | 0 |  |  | 0
Shifting | 290 | 0 |  |  | 0
Reaming | 290 | 0 |  |  | 0
Clearing Rods | 290 | 0 |  |  | 0
Changing Drill Type | 290 | 0 |  |  | 0
Consumables
PVC m |  |  | 21.5 | 0 | 0
Foamit kg |  |  | 9.62 | 0 | 0
Drill Foam l |  |  | 20 | 0 | 0
Budgeted Total Hrs |  | 0
Sub Total |  |  |  |  | 2800 | 14
Geology General |  |  | Cost/unit | Total Number | Total
|  |  | Estimate | Units | Cost
Geol Consumables
Sample Bags 1m Plastics |  |  | 0.56 | 58 | 32.48
Calico Sample Bags |  |  | 0.35 | 0 | 0
Sample Bags 1m Calicos |  |  | 0.8 | 0 | 0
Drill Chips |  |  | 1.5 | 0 | 0
Survey Pegs |  |  | 0.9 | 50 | 45
Sample Books |  |  | 3.8 | 0 | 0
Flagging Tape |  |  | 3 | 0 | 0
Bucket |  |  | 8.3 | 0 | 0
Sieve |  |  | 10 | 0 | 0
Poly Chain |  |  | 172 | 0 | 0
Earplugs |  |  | 0.22 | 0 | 0
Water Cooler |  |  | 19.15 | 0 | 0
Acid Dropper |  |  | 0.9 | 0 | 0
Safety Dust Mask |  |  | 5 | 0 | 0
Marker Pens |  |  | 2.25 | 5 | 11.25
Polyweave Bags |  |  | 0.75 | 0 | 0
Sub Total |  |  |  |  | 88.73 | 0.44365
Management | Cost/day | Total Days |  |  | Total Cost
Supervision | 500 | 6 |  |  | 3000
Field Technician | 250 | 3 |  |  | 750
Sub Total |  |  |  |  | 3750 | 18.75
Site General |  | Total Days |  |  | Total Cost
Site Rehabilitation | 500 | 0 |  |  | 0
Site Preparation | 800 | 0 |  |  | 0
Geotechnical |  |  |  |  | 0
Survey | 1500 | 0 |  |  | 0
Hydrology |  |  |  |  | 0
Metallurgy | 1000 | 0 |  |  | 0
Archaeology (Native Title) | 500 | 0 |  |  | 0
Subtotal |  |  |  |  | 0 | 0
Programme Subtotal |  |  |  |  | 9785.83 | 48.9291
Contingency 10% |  |  |  |  | 978.583
Total |  |  |  |  | 10764.413 | 53.8221
Note * Equates to fixed Cost

## Return Projections
Project Return on Capital from Exploration
Metres Drilled to Tonnes Defined
Project Cost Estimates |  | Cost/m | Cost/t
Metres Drilled | 25000 | 80
Prefeasability
Feasability
Est. Total Cost to Final Development
Projected Value Of Project
| Tonnes | Grade | Metal | LME Price
| Reserves |  | Tonnes/ozs | Per t/ozs
Lead | 540000 | 8% | 43200 | 450 | 19440000
Zinc | 540000 | 9% | 48600 | 1100 | 53460000
Silver | 540000 | 80g/t | 1388933.5434 | 5 | 6944667.7169
79844667.7169