## Sheet1
EL28843 | Original | Hole ID | Project Area | Section | MGA North | MGA East | MRL | Type | Depth | Collar | Hole |  | Comments | Photo
[10 empty] | status | rehab status |  |  | sequence
Helen Springs:
EL28843 | EL23495 | HSRC0040 | Helen Springs | 7961030 | 7961055.1 | 393364.9 | 259.1 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 1 | 2
EL28843 | EL23495 | HSRC0041 | Helen Springs |  | 7961048.8 | 393466.3 | 257.7 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 3 | 4
EL28843 | EL23495 | HSRC0031 | Helen Springs |  | 7961049.54 | 393549.78 | 256.677 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 5 | 6
EL28843 | EL23495 | HSRC0032 | Helen Springs |  | 7961047.73 | 393651.01 | 256.575 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 7 | 8
EL28843 | EL23495 | HSRC0033 | Helen Springs |  | 7961054.91 | 393749.05 | 257.173 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 9 | 10
EL28843 | EL23495 | HSRC0042 | Helen Springs |  | 7961061.5 | 393858 | 256.7 | RC | 54 | PLUG | Completed | 2014-07-28 | Revegetated | 11 | 12
EL28843 | EL23495 | EUPC 11 | Helen Springs |  | 7961015 | 393919 | 258 | PC | 16 | PLUG | Completed | 2014-07-28 | Overgrown | 28
EL28843 | EL23495 | HSRC0043 | Helen Springs |  | 7961036.8 | 393972.7 | 257.3 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 13 | 14
EL28843 | EL23495 | HSRC0044 | Helen Springs |  | 7961027.5 | 394060.7 | 255.6 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 15 | 16
EL28843 | EL23495 | HSRC0045 | Helen Springs |  | 7961020.3 | 394157.9 | 253.9 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 17 | 18
EL28843 | EL23495 | HSRC0046 | Helen Springs |  | 7961012.7 | 394252.7 | 254.9 | RC | 54 | PLUG | Completed | 2014-07-28 | Revegetated | 19 | 20
EL28843 | EL23495 | HSRC0047 | Helen Springs |  | 7961004.8 | 394351.3 | 255.9 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 21 | 22
EL28843 | EL23495 | HSRC0048 | Helen Springs |  | 7960997.3 | 394447.7 | 255.7 | RC | 78 | PLUG | Completed | 2014-07-28 | Revegetated | 23 | 24
EL28843 | EL23495 | HSRC0049 | Helen Springs |  | 7960978.4 | 394636.9 | 254 | RC | 54 | PLUG | Completed | 2014-07-28 | Revegetated | 25 | 26 | 27
EL28843 | EL23495 | HSRC0006 | Helen Springs | 7960945 | 7960942.68 | 393612.01 | 257.872 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 29 | 30
EL28843 | EL23495 | HSRC0005 | Helen Springs |  | 7960945.06 | 393648.05 | 257.566 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 31 | 32
EL28843 | EL23495 | HSRC0011 | Helen Springs |  | 7960944.47 | 393688.7 | 257.309 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 33 | 34
EL28843 | EL23495 | HSRC0050 | Helen Springs | 7960910 | 7960913.9 | 393539.6 | 258.9 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 35 | 36
EL28843 | EL23495 | HSRC0051 | Helen Springs |  | 7960909.5 | 393554.2 | 258.7 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 37 | 38
EL28843 | EL23495 | HSRC0007 | Helen Springs |  | 7960900.41 | 393577.96 | 258.448 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 41 | 42
EL28843 | EL23495 | HSRC0052 | Helen Springs | 7960870 | 7960870.8 | 393548.3 | 258.5 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 43 | 44
EL28843 | EL23495 | HSRC0008 | Helen Springs |  | 7960865.79 | 393576.08 | 258.655 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 45 | 46
EL28843 | EL23495 | EUPC 10 | Helen Springs |  | 7960868 | 393581 | 257 | PC | 16 |  | Not found | 2014-07-28 | Buried
EL28843 | EL23495 | HSRC0009 | Helen Springs |  | 7960869.63 | 393603.74 | 258.381 | RC | 72 | PLUG | Completed | 2014-07-28 | Revegetated | 47 | 48
EL28843 | EL23495 | HSRC0010 | Helen Springs |  | 7960875.64 | 393646.8 | 258.162 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 49 | 50
|  |  | North costean | [7 empty] | N/A | 2014-07-28 | North costean - backfilled & revegetating | 51 | 52 | 53
EL28843 | EL23495 | EUPC 8 | Helen Springs | 7960845 | 7960844 | 393577 | 257 | PC | 16 |  | Not found | 2014-07-28 | Buried
EL28843 | EL23495 | HSRC0004 | Helen Springs | 7960835 | 7960835.65 | 393529.58 | 259.149 | RC | 72 | PLUG | Completed | 2014-07-28 | Revegetated | 54 | 55
EL28843 | EL23495 | HSRC0053 | Helen Springs |  | 7960833.3 | 393551.9 | 258.6 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 56 | 57
EL28843 | EL23495 | HSRC0003 | Helen Springs |  | 7960835.58 | 393576.91 | 258.861 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 58 | 59
EL28843 | EL23495 | HSRC0054 | Helen Springs |  | 7960832.5 | 393597.2 | 259.4 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 60 | 61
EL28843 | EL23495 | HSRC0055 | Helen Springs |  | 7960833.8 | 393617.2 | 259.7 | RC | 6 | PLUG | Completed | 2014-07-28 | Revegetated | 62 | 63
EL28843 | EL28843 | HSRC0077 | Helen Springs | 7960823 | 7960824.5 | 393564.8 | 257.6 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated. Marked HSRC0076 | 64 | 65
EL28843 | EL28843 | HSRC0076 | Helen Springs |  | 7960821.8 | 393579.2 | 257.8 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated. Marked HSRC0075 | 66 | 67
EL28843 | EL23495 | EUPC 9 | Helen Springs | 7960810 | 7960809 | 393597 | 257 | PC | 12 |  | Not found | 2014-07-28 | Buried
EL28843 | EL23495 | HSRC0056 | Helen Springs | 7960800 | 7960803.6 | 393545.1 | 258.6 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 68 | 69
EL28843 | EL28843 | HSRC0074 | Helen Springs |  | 7960801.2 | 393561.1 | 257.5 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 70 | 71
EL28843 | EL23495 | HSRC0057 | Helen Springs |  | 7960799.4 | 393577.1 | 257.1 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 72 | 73
EL28843 | EL23495 | HSRC0058 | Helen Springs |  | 7960798 | 393603.5 | 257.1 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 74 | 75
EL28843 | EL23495 | HSRC0013 | Helen Springs | 7960790 | 7960790.92 | 393467.7 | 260.072 | RC | 48 | PLUG | Completed | 2014-07-28 | Overgrown | 76 | 77
EL28843 | EL23495 | HSRC0059 | Helen Springs | 7960775 | 7960782.1 | 393536.6 | 259.1 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 78 | 79
EL28843 | EL23495 | HSRC0060 | Helen Springs |  | 7960778.9 | 393559 | 259.2 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 80 | 81
EL28843 | EL28843 | HSRC0075 | Helen Springs |  | 7960775 | 393573.4 | 258.5 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 82 | 83
EL28843 | EL23495 | HSRC0012 | Helen Springs |  | 7960772.71 | 393586.72 | 259.077 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 84 | 85
EL28843 | EL28843 | HSRC0080 | Helen Springs | 7960740 | 7960741.3 | 393558.4 | 257.9 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 86 | 87
EL28843 | EL28843 | HSRC0079 | Helen Springs |  | 7960741.8 | 393578.2 | 257.7 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated | 88 | 89
EL28843 | EL28843 | HSRC0078 | Helen Springs |  | 7960742.3 | 393595 | 257.6 | RC | 42 | PLUG | Completed | 2014-07-28 | Revegetated. Hole partly collapsed | 90 | 91
EL28843 | EL23495 | EUPC 7 | Helen Springs | 7960715 | 7960715 | 393345 | 258 | PC | 27 |  | Not found | 2014-07-28
EL28843 | EL28843 | HSRC0082 | Helen Springs | 7960700 | 7960701.8 | 393567.9 | 258.4 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated. Collapsed hole | 92 | 93
EL28843 | EL28843 | HSRC0081 | Helen Springs |  | 7960701.5 | 393587.1 | 257.9 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 94 | 95
EL28843 | EL28843 | HSRC0083 | Helen Springs | 7960600 | 7960601 | 393567.2 | 258.3 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 96 | 97
EL28843 | EL28843 | HSRC0084 | Helen Springs |  | 7960600.2 | 393586.5 | 258.3 | RC | 30 | PLUG | Completed | 2014-07-28 | Revegetated | 98 | 99
EL28843 | EL23495 | EUPC 12 | Helen Springs | 7960550 | 7960548 | 393767 | 256 | PC | 24 | PLUG | Completed | 2014-07-28 | Revegetated | 100 | 101
EL28843 | EL23495 | HSRC0061 | Helen Springs | 7960500 | 7960498.6 | 393343.8 | 262 | RC | 36 | PLUG | Completed | 2014-07-28 | Revegetated | 104 | 105
EL28843 | EL23495 | HSRC0035 | Helen Springs |  | 7960501.47 | 393395.72 | 260.29 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 106 | 107
EL28843 | EL23495 | HSRC0036 | Helen Springs |  | 7960498.45 | 393490.99 | 259.188 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 108 | 109
EL28843 | EL28843 | HSRC0085 | Helen Springs |  | 7960500.3 | 393557.3 | 259.5 | RC | 36 | PLUG | Completed | 2014-07-28 | Open track. Marked HSRC0087 | 110 | 111
EL28843 | EL28843 | HSRC0086 | Helen Springs |  | 7960499.4 | 393576.8 | 259.1 | RC | 30 | PLUG | Completed | 2014-07-28 | Open track | 112 | 113
EL28843 | EL28843 | HSRC0087 | Helen Springs |  | 7960499.3 | 393597.4 | 258.8 | RC | 30 | PLUG | Completed | 2014-07-28 | Open track. Marked HSRC0085 | 114 | 115
EL28843 | EL23495 | HSRC0062 | Helen Springs |  | 7960498 | 393648.5 | 258.7 | RC | 30 | PLUG | Completed | 2014-07-28 | Open track | 116 | 117
EL28843 | EL23495 | HSRC0034 | Helen Springs | 7960485 | 7960484.64 | 393292.4 | 261.292 | RC | 60 | PLUG | Completed | 2014-07-28 | Revegetated | 102 | 103
EL28843 | EL23495 | HSRC0063 | Helen Springs |  | 7960487.2 | 393838.9 | 258.1 | RC | 6 | PLUG | Completed | 2014-07-28 | Revegetated | 118 | 119
EL28843 | EL23495 | EUPC 5 | Helen Springs | 7960430 | 7960426 | 393342 | 259 | PC | 32 |  | Not found | 2014-07-28
EL28843 | EL23495 | EUPC 1 | Helen Springs |  | 7960437 | 393568 | 258 | PC | 18 |  | Not found | 2014-07-28
EL28843 | EL23495 | HSRC0015 | Helen Springs |  | 7960431.23 | 393621.78 | 258.8 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 126 | 127
EL28843 | EL23495 | HSRC0014 | Helen Springs |  | 7960421.49 | 393663.6 | 258.426 | RC | 48 | PLUG | Completed | 2014-07-28 | Revegetated | 128 | 129
EL28843 | EL28843 | HSRC0088 | Helen Springs | 7960400 | 7960400.9 | 393578.3 | 259.9 | RC | 30 | PLUG | Completed | 2014-07-28 | Open track | 120 | 121
EL28843 | EL28843 | HSRC0089 | Helen Springs |  | 7960400.7 | 393597.9 | 259.8 | RC | 24 | PLUG | Completed | 2014-07-28 | Open track | 122 | 123
EL28843 | EL28843 | HSRC0090 | Helen Springs |  | 7960400.7 | 393616.8 | 259.2 | RC | 24 | PLUG | Completed | 2014-07-28 | Open track | 124 | 125
EL28843 | EL23495 | EUPC 6 | Helen Springs | 7960350 | 7960352 | 393267 | 262 | PC | 35 |  | Not found | 2014-07-28
|  |  | South costean | [7 empty] | N/A | 2014-07-29 | North costean - backfilled & revegetating | 1 | 2
EL28843 | EL23495 | HSRC0002 | Helen Springs | 7960320 | 7960319.42 | 393618.99 | 258.87 | RC | 42 | PLUG | Completed | 2014-07-29 | Revegetated | 3 | 4
EL28843 | EL23495 | HSRC0001 | Helen Springs |  | 7960325.66 | 393665.34 | 258.467 | RC | 78 | PLUG | Completed | 2014-07-29 | Revegetated | 5 | 6
EL28843 | EL23495 | HSRC0064 | Helen Springs | 7960300 | 7960301.3 | 393461.8 | 262.1 | RC | 54 | PLUG | Completed | 2014-07-29 | Partly revegetated | 7 | 8
EL28843 | EL23495 | HSRC0065 | Helen Springs |  | 7960292.8 | 393581.1 | 259.8 | RC | 36 | PLUG | Completed | 2014-07-29 | Open track | 9 | 10
EL28843 | EL28843 | HSRC0091 | Helen Springs |  | 7960292.1 | 393685.1 | 258.3 | RC | 24 | PLUG | Completed | 2014-07-29 | Open track | 11 | 12
EL28843 | EL23495 | HSRC0016 | Helen Springs |  | 7960299.96 | 393703.27 | 258.313 | RC | 48 | PLUG | Completed | 2014-07-29 | Revegetated | 13 | 14
EL28843 | EL23495 | HSRC0066 | Helen Springs |  | 7960300.7 | 393814.1 | 260.1 | RC | 6 | PLUG | Completed | 2014-07-29 | Revegetated | 15 | 16
EL28843 | EL23495 | HSRC0017 | Helen Springs | 7960260 | 7960260.42 | 393655.84 | 258.607 | RC | 42 | PLUG | Completed | 2014-07-29 | Revegetated | 17 | 18
EL28843 | EL23495 | EUPC 2 | Helen Springs | 7960240 | 7960238 | 393190 | 267 | PC | 27 |  | Not found | 2014-07-29
EL28843 | EL23495 | EUPC 3 | Helen Springs |  | 7960248 | 393272 | 264 | PC | 36 |  | Not found | 2014-07-29
EL28843 | EL23495 | HSRC0018 | Helen Springs |  | 7960241.2 | 393718.91 | 258.423 | RC | 48 | PLUG | Completed | 2014-07-29 | Revegetated | 19 | 20
EL28843 | EL23495 | EUPC 4 | Helen Springs | 7960115 | 7960114 | 393545 | 261 | PC | 29 |  | Not found | 2014-07-29
EL28843 | EL23495 | HSRC0067 | Helen Springs | 7960000 | 7959998.2 | 393251.2 | 266.9 | RC | 30 | PLUG | Completed | 2014-07-29 | Overgrown | 21 | 22
EL28843 | EL23495 | HSRC0068 | Helen Springs |  | 7959998.7 | 393459 | 264.1 | RC | 12 | PLUG | Completed | 2014-07-29 | Overgrown | 23 | 24
EL28843 | EL23495 | HSRC0069 | Helen Springs |  | 7960002.5 | 393654 | 260.6 | RC | 6 | PLUG | Completed | 2014-07-29 | Revegetated | 25 | 26
EL28843 | EL23495 | HSRC0070 | Helen Springs |  | 7960001 | 393850.8 | 266.8 | RC | 6 | PLUG | Completed | 2014-07-29 | Revegetated | 27 | 28
EL28843 | EL23495 | HSRC0071 | Helen Springs |  | 7959999.5 | 394052 | 257.6 | RC | 6 | PLUG | Completed | 2014-07-29 | Revegetated | 29 | 30
EL28843 | EL23495 | HSRC0072 | Helen Springs |  | 7959997.8 | 394254.2 | 259.6 | RC | 6 | PLUG | Completed | 2014-07-29 | Overgrown | 31 | 32
EL28843 | EL23495 | HSRC0073 | Helen Springs |  | 7959997.1 | 394450.6 | 265.8 | RC | 6 | PLUG | Completed | 2014-07-29 | Revegetated | 33 | 34
EL28843 | EL23495 | HSRC0037 | Helen Springs | 7959050 | 7959049.38 | 393401.44 | 264.819 | RC | 60 | PLUG | Completed | 2014-07-29 | Overgrown | 35 | 36
EL28843 | EL23495 | HSRC0038 | Helen Springs |  | 7959048.64 | 393499.34 | 263.917 | RC | 60 | PLUG | Completed | 2014-07-29 | Overgrown | 37 | 38
EL28843 | EL23495 | HSRC0039 | Helen Springs |  | 7959050.45 | 393599.27 | 262.815 | RC | 60 | PLUG | Completed | 2014-07-29 | Revegetated | 39 | 40
EL28843 | EL23495 | HSRC0028 | Helen Springs | nth-sth | 7958702.87 | 395152.14 | 265.195 | RC | 90 | PLUG | Completed | 2014-07-29 | Revegetated | 45 | 46
EL28843 | EL23495 | HSRC0029 | Helen Springs |  | 7958353.63 | 395195.47 | 269.701 | RC | 78 | PLUG | Completed | 2014-07-29 | Revegetated | 43 | 44
EL28843 | EL23495 | HSRC0030 | Helen Springs |  | 7958110.57 | 395251.32 | 270.305 | RC | 90 | PLUG | Completed | 2014-07-29 | Revegetated | 41 | 42
EL28843 |  | 94 | [7 empty] | 84