## Sheet1
Oct | Nov | Dec | Totals |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Totals
Heavy Liquid Separation Tests
Gravity Survey
Drilling Program to upgrade
inferred resource to indicated
resource. 5 Million Tonnes
|  |  |  | Bulk Sampling / Trenching | Apr: 50000; May: 50000; Jun: 50000; Jul: 50000 | 200000
Heavy Liquid Tests
|  |  |  | Fly area for Survey Control | Jul: 30000 | 30000
10150 | 150 |  | 10300 | Acquisitions to complete tenement holdings
143300 | 14850 | 7350 | 165500 | Drilling Program to establish
measured reserves of 10 million Tonnes
Indicated Resource of 17 million tonnes
|  |  |  | Large Diameter Diamond Core Drilling | Apr: 80000; May: 80000; Jun: 80000 | 240000
|  |  |  | Analysis | Apr: 25000; May: 25000; Jun: 25000 | 75000
|  |  |  | Metallurgical Test Work | Jun: 20000; Jul: 20000 | 40000
|  |  | 0 | Payments to Traditional Owners
0
20000 | 20000 | 20000 | 60000 | Mining Studies
|  |  |  | Environmental Impact Statement | Jan: 15000; Feb: 15000; Mar: 15000; Apr: 15000 | 60000
Marketing Arrangements
|  |  |  | Process Plant Design | Jun: 15000; Jul: 15000 | 30000
Engineering Design of
|  |  |  | Shiploading, Stockpiling, | Apr: 25000; May: 25000; Jun: 25000 | 75000
Reclaiming Facilities
Feasibility Study
Mine Design / Environmental approvals
|  |  |  | Negotiate Mining Agreement with Native Title Claimants | Jan: 20000; Feb: 20000; Mar: 20000; Apr: 20000 | 80000
|  |  |  | Negotiate road corridor access to rail line | Jan: 20000; Feb: 20000; Mar: 20000; Apr: 20000 | 80000
|  |  |  | Complete Licensing Arrangements with NT Government | Jan: 10000; Feb: 10000; Mar: 10000; Apr: 10000 | 40000
|  |  |  | Negotiate contracts for building port facilities | 5000 | 5000 | 5000 | 5000 | 5000 |  |  |  | 25000
|  |  |  | Negotiate contracts for building mine facilities | Mar: 5000; Apr: 5000; May: 5000 | 15000
|  |  |  | Negotiate mining and processing contracts | Apr: 5000; May: 5000; Jun: 5000; Jul: 5000 | 20000
|  |  |  | Negotiate rail freight contracts | Mar: 10000; Apr: 10000 | 20000
173450 | 35000 | 27350 | 235800 |  | 70000 | 70000 | 85000 | 270000 | 195000 | 220000 | 120000 | 0 | 1030000