## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-24
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Pull XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 39 |  | Assistant |  | Stephen Brabin
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FTHP | 242 | 278 | Serial and Type | 70574-1 | WMG EMR |  | 8168 /8169
Pcsg | 381 | 358 | Gas Detector | Dragger | Pipe Package
Icsg | 47 | 55 | Serial Number | ARWE-0438 | Flowprover
Scsg | 0 | 0 | Wellhead Recorder : Crystal |  | S/line Truck Km's |  | 1
[5 empty] | Crane Truck KM's |  | 38
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. Shut in well, Disconnect wellhead recorder. R/up Wireline. Closed SSD at 4936'WLD (4952'KB) and closed SSD at 4786'WLD (4802'KB). Retrieved P-prong from PXN-plug body at XN-nipple @4954'WLD (4970'KB). Retrieved PXN-plug body with 2 x EMR from XN-nipple at 4956'WLD (4972'KB). Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB). Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Download EMR gauges/ wellhead recorder; service wireline tools. Attend Santos weekly safety meeting. Generate report.
Forward Plan : |  | East Mereenie 41 - Zone Isolation Test.
Time | Description
0600 | Attend morning meeting and obtain wellhead handover permit.
0650 | Depart from yard.
0700 | Arrive location; TBM & gas test (LEL=0%; OXY.=20.9%). FTHP=242psi; PCP=381psi.
0715 | Shut in well and monitor for 2 HRS, CITHP=369psi.
0915 | Disconnect wellhead recorder and Rig up wireline equipment onto wellhead.
0940 | RIH 2" B-shifting tool and closed SSD at 4936'WLD (4952'KB); inject THP to 511psi from PCP, closed SSD at
4786'WLD (4802'KB). pull out of hole, pin not sheared.
1040 | RIH 2" SB and retrieved P-prong from PXN plug body at XN-nipple @ 4954'WLD (4970'KB), pull out of hole.
CITHP dropped from 503psi to 480psi.
Monitor for 1 hour, THP dropped from 455psi.
1230 | RIH 2" GS and retrieved PXN-plug body with EMR gauges from XN-nipple at 4956'WLD (4970'KB), pull out of hole.
On surface and disconnect EMR gauges, battery disconnect at 1325HRS.
1330 | RIH 2" B-shifting tool and Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB), pull out of
hole, pin not sheared.
1400 | Rig down all wireline equipment from well head. CITHP=409psi; PCP=410psi
1430 | Flow well back to production line with gaslift injector. FTHP=278psi; PCP=358psi.
1440 | Depart from location.
1450 | Arrive yard and download EMR data; service wireline tools.
1600 | Attend Santos weekly safety meeting.
1730 | Continue re-dress wireline tools prior use on EM-41.
1800 | Generate report.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18001'
Runs |  | 4 | Wire Cut | Nil | Balance |  | 18001'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-24
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Pull XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 39 |  | Assistant |  | Stephen Brabin
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 242 | 278 | Serial and Type | 70574-1 | Crane |  | 8168 /8169
Pcsg | 381 | 358 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 47 | 55 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 1
|  |  | Toyota Km's | 0 | Truck Km's |  | 38
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. Shut in well, Disconnect wellhead recorder. R/up Wireline. Closed SSD at 4936'WLD (4952'KB) and closed SSD at 4786'WLD (4802'KB). Retrieved P-prong from PXN-plug body at XN-nipple @4954'WLD (4970'KB). Retrieved PXN-plug body with 2 x EMR from XN-nipple at 4956'WLD (4972'KB). Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB). Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Download EMR gauges/ wellhead recorder; service wireline tools. Attend Santos weekly safety meeting. Generate report.
Forward Plan : |  | East Mereenie 41 - Zone Isolation Test.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-24
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 39
Type of operation | Pull XN-plug w/EMR; Open SSD.
24 Hour summary | Morning meeting. Depart to location, TBM; gas test. Shut in well, Disconnect wellhead recorder. R/up Wireline. Closed SSD at 4936'WLD (4952'KB) and closed SSD at 4786'WLD (4802'KB). Retrieved P-prong from PXN-plug body at XN-nipple @4954'WLD (4970'KB). Retrieved PXN-plug body with 2 x EMR from XN-nipple at 4956'WLD (4972'KB). Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB). Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Download EMR gauges/ wellhead recorder; service wireline tools. Attend Santos weekly safety meeting. Generate report.
Forward plan | East Mereenie 41 - Zone Isolation Test.
Archive file name | east_mereenie_39_2008-05-24_pull_xn-plug_w/emr;_open_ssd_wl46.xls