## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-23
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Set XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 39 |  | Assistant |  | Jonathan M. / Steve
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FITHP | 174 | 245 | Serial and Type | 70574-1 | WMG EMR |  | 8168 /8169
Pcsg | 290 | 280 | Gas Detector | Dragger | Pipe Package
Icsg | 46 | 47 | Serial Number | ARWE-0438 | Flowprover
Scsg | 0 | 0 | Wellhead Recorder : Crystal |  | S/line Truck Km's |  | 9
[5 empty] | Crane Truck KM's |  | 36
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Closed SSD at 4936'WLD (4952'KB); and closed SSD at 4786'WLD (4802'KB), pull out of hole. Set PXN-plug with EMR x 2 in XN-nipple at 4956'WLD (4972'KB), pull out of hole. Bled THP from 377 PSI to 330 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB), pull out of hole. Rig down wireline. Hook up wellhead pressure recorder on wellhead. Flow well to production line with gaslift injector. Depart from location, generate report.
Forward Plan : |  | East Mereenie 39 - Zone Isolate Test -- Retrieve PXN-plug with EMR and close / open SSD.
Time | Description
0600 | Attend morning meeting and obtain wellhead handover permit.
0650 | Depart from yard.
0710 | Arrive location; TBM & gas test (LEL=0%; OXY.=20.9%). Shut in well at 0720HRS.
0725 | Rig up wireline equipment onto wellhead and pressure tested against CITHP.
0750 | RIH 2" B-shifting tool and close SSD at 4936'WLD (4952'KB); and while pull out of hole closed SSD at 4786'WLD
(4802'KB), pull out of hole. Encountered wax on tool and tool string.
0850 | Set-up PXN-plug body with 2 x EMR. Battery connect at 0909 HRS.
0915 | Open Master valve.
0925 | RIH 1.875" PXN-plug body with 2 x EMR and set in XN-nipple at 4956'WLD (4972'KB); pull out of hole.
1100 | RIH 2" SB with 2" P-prong and set in PXN-plug body at XN-nipple @ 4954'WLD (4970'KB); pull out of hole.
1140 | Bled CITHP 377 PSI to 330'PSI and observe for 1 HR, No build up. Confirmed SSD's closed and PXN-plug hold.
1245 | RIH 2" B-shifting tool, unable to run in hole at 218'WLD, pull out of hole, encountered wax on tool and tool string.
1400 | Run in hole 1.85" gauge ring till top of P-prong at 4954'WLD (4970'KB), pull out of hole.
1435 | RIH 2" B-shifting tool and open SSD at 4786'WLD (4802'KB) THP build up from 330psi to 365psi. Inject THP from
PCP to 472psi, and continue to run in hole and open SSD at 4936'WLD (4952'KB), THP dropped from 472psi to
390psi. pull out of hole.
1550 | Rig down all wireline equipment from well head.
1620 | Hook-up wellhead recorder.
1630 | Flow well back to production line with gaslift injector.
1645 | Depart from location.
1700 | Arrived yard and generate report.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18001'
Runs |  | 6 | Wire Cut | Nil | Balance |  | 18001'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-23
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Set XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 39 |  | Assistant |  | Jonathan M. / Steve
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 174 | 245 | Serial and Type | 70574-1 | Crane |  | 8168 /8169
Pcsg | 290 | 280 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 46 | 47 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 9
|  |  | Toyota Km's | 0 | Truck Km's |  | 36
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Closed SSD at 4936'WLD (4952'KB); and closed SSD at 4786'WLD (4802'KB), pull out of hole. Set PXN-plug with EMR x 2 in XN-nipple at 4956'WLD (4972'KB), pull out of hole. Bled THP from 377 PSI to 330 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB), pull out of hole. Rig down wireline. Hook up wellhead pressure recorder on wellhead. Flow well to production line with gaslift injector. Depart from location, generate report.
Forward Plan : |  | East Mereenie 39 - Zone Isolate Test -- Retrieve PXN-plug with EMR and close / open SSD.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-23
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 39
Type of operation | Set XN-plug w/EMR; Open SSD.
24 Hour summary | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Closed SSD at 4936'WLD (4952'KB); and closed SSD at 4786'WLD (4802'KB), pull out of hole. Set PXN-plug with EMR x 2 in XN-nipple at 4956'WLD (4972'KB), pull out of hole. Bled THP from 377 PSI to 330 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4786'WLD (4802'KB) and open SSD at 4936'WLD (4952'KB), pull out of hole. Rig down wireline. Hook up wellhead pressure recorder on wellhead. Flow well to production line with gaslift injector. Depart from location, generate report.
Forward plan | East Mereenie 39 - Zone Isolate Test -- Retrieve PXN-plug with EMR and close / open SSD.
Archive file name | east_mereenie_39_2008-05-23_set_xn-plug_w/emr;_open_ssd_wl46.xls