## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-17
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Set XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FITHP | 223 | 230 | Serial and Type | 70574-1 | WMG EMR |  | 8168 /8169
Pcsg | 427 | 452 | Gas Detector | Dragger | Pipe Package
Icsg | 73 | 73 | Serial Number | ARWE-0438 | Flowprover
Scsg |  |  | Wellhead Recorder : Crystal |  | S/line Truck Km's |  | 1
[5 empty] | Crane Truck KM's |  | 20
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Set PXN-plug with EMR x 2 in XN-nipple at 5130'WLD (5144'KB), pull out of hole. Closed SSD at 5106'WLD (5120'KB); and confirm SSD at 4966'WLD (4980'KB) closed, pull out of hole. Bled THP from 454 PSI to 408 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4966'WLD (4980'KB) and SSD at 5106'WLD (5120'KB); pull out of hole. Open back SSD at 4966'WLD (4980'KB). Rig down wireline from wellhead. Hook up wellhead pressure recorder on wellhead. Flow well to production line. Depart from location, Service wireline tools and generate report.
Forward Plan : |  | East Mereenie 40 - Zone Isolate Test -- Retrieve PXN-plug with EMR and open SSD.
Time | Description
0600 | Attend morning meeting and obtain wellhead handover permit.
0630 | Service PXN-plug and assemble to x-line running tool. Depart from yard.
0730 | Arrive location; TBM & gas test (LEL=0%; OXY.=20.9%). Shut in well at 0800HRS.
Rig up wireline equipment onto wellhead and pressure tested against CITHP.
Set-up1.875" PXN-plug body with 2 x EMR. Battery connect at 0823 HRS.
0842 | Open Master valve.
0850 | RIH 1.875" PXN-plug body with 2 x EMR and set in XN-nipple at 5130'WLD (5144'KB); pull out of hole.
0950 | RIH 2" SB with 2" P-prong and set in PXN-plug body at XN-nipple @ 5129'WLD (5143'KB); pull out of hole.
CITHP=463; PCP=427PSI.
1030 | RIH 2" B-shifting tool and close SSD at 5106'WLD (5120'KB); and confirm SSD at 4966'WLD (4980'KB) Closed.
Pull out of hole. CITHP=454PSI; PCP=423PSI.
1125 | Bled CITHP 454 PSI to 408 PSI and observe for 1 HR, No build up. Confirmed SSD's closed and PXN-plug hold.
1240 | RIH 2" B-shifting tool and open SSD at 4966'WLD (4980'KB) and SSD at 5106'WLD (5120'KB); pull out of hole.
1325 | RIH 2" B-shifting tool and close SSD 4966'WLD (4980'KB), pull out of hole, Pin not sheared.
1345 | Rig out all wireline equipment from wellhead.
Hook-up Crystal wellhead recorder onto wellhead. Gauge recorder ON at 1406HRS.
1425 | Flow well on to production line. CITHP=453psi; PCP=452psi; ICP=73psi.
FTHP=230psi; PCP=452PSI; ICP=73psi.
1500 | Depart from location.
1525 | Arrive Yard;
1530 | Service wireline tools and generate report.
1700 | End of day.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18181'
Runs |  | 5 | Wire Cut | Nil | Balance |  | 18181'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-17
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Set XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 223 | 230 | Serial and Type | 70574-1 | Crane |  | 8168 /8169
Pcsg | 427 | 452 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 73 | 73 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 1
|  |  | Toyota Km's | 0 | Truck Km's |  | 20
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Set PXN-plug with EMR x 2 in XN-nipple at 5130'WLD (5144'KB), pull out of hole. Closed SSD at 5106'WLD (5120'KB); and confirm SSD at 4966'WLD (4980'KB) closed, pull out of hole. Bled THP from 454 PSI to 408 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4966'WLD (4980'KB) and SSD at 5106'WLD (5120'KB); pull out of hole. Open back SSD at 4966'WLD (4980'KB). Rig down wireline from wellhead. Hook up wellhead pressure recorder on wellhead. Flow well to production line. Depart from location, Service wireline tools and generate report.
Forward Plan : |  | East Mereenie 40 - Zone Isolate Test -- Retrieve PXN-plug with EMR and open SSD.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-17
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 40
Type of operation | Set XN-plug w/EMR; Open SSD.
24 Hour summary | Morning meeting. Obtain well site handover permit. Depart to location, TBM; gas test. Shut in well, R/up Wireline. Set PXN-plug with EMR x 2 in XN-nipple at 5130'WLD (5144'KB), pull out of hole. Closed SSD at 5106'WLD (5120'KB); and confirm SSD at 4966'WLD (4980'KB) closed, pull out of hole. Bled THP from 454 PSI to 408 PSI and observed for 1 HR, confirm SSD's and plug hold. Open SSD at 4966'WLD (4980'KB) and SSD at 5106'WLD (5120'KB); pull out of hole. Open back SSD at 4966'WLD (4980'KB). Rig down wireline from wellhead. Hook up wellhead pressure recorder on wellhead. Flow well to production line. Depart from location, Service wireline tools and generate report.
Forward plan | East Mereenie 40 - Zone Isolate Test -- Retrieve PXN-plug with EMR and open SSD.
Archive file name | east_mereenie_40_2008-05-17_set_xn-plug_w/emr;_open_ssd_wl46.xls