## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-13
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Drifts Runs
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FITHP | 230 | 250 | Serial and Type | 70574-1 | WMG EMR
Pcsg | 424 | 424 | Gas Detector | Dragger | Pipe Package
Icsg |  |  | Serial Number | ARWE-0438 | Flowprover
Scsg | 73 | 68 | TOYOTA |  | S/line Truck Km's |  | 1
[5 empty] | Crane Truck KM's |  | 16
SEQUENCE OF EVENTS
24 Hr Summary : |  | Obtain work permit. Depart to location; TBM; gas test. Shut in well. Rig up wireline equipment onto wellhead. Run in hole 1.75" Gauge Ring to HUD at 5358'WLD (5372'RKB), pull out of hole. Run in hole 1.85" gauge Ring and tag XN nipple at 5129'WLD (5143'RKB); Pull out of hole. Rig out wireline equipment from wellhead. Flow well back online. depart from location. Hand back work permit and generate report.
Forward Plan : |  | East Mereenie 38 / 39 / 41 - Drifts Runs.
Time | Description
1230 | Obtain work permit.
1300 | Depart to location.
1320 | Arrive location. TBM; gas test: LEL=0%; Oxy.=20.9
1330 | Shut in well. (FTHP=230 PSI; PCP=424PSI).
Rig up wireline equipment onto wellhead. Pressure tested lubricators against CITHP.
1400 | Run in hole 1.75" Gauge Ring to HUD at 5358'WLD (5372'RKB), pull out of hole.
1430 | Run in hole 1.85" gauge Ring and tag XN nipple at 5129'WLD (5143'RKB); Pull out of hole.
1510 | Rig out wireline equipment from wellhead. (SITHP=486PSI; PCP=424PSI)
1540 | Flow well back online.
1600 | Depart from location, and hand back work permit.
1630 | Back to Yard and generate report.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18181'
Runs |  | 2 | Wire Cut | Nil | Balance |  | 18181'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-13
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Drifts Runs
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 230 | 250 | Serial and Type | 70574-1 | Crane |  | 0
Pcsg | 424 | 424 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 0 | 0 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 73 | 68 | Toyota | 0 | Truck |  | 1
|  |  | Toyota Km's | 0 | Truck Km's |  | 16
SEQUENCE OF EVENTS
24 Hr Summary : |  | Obtain work permit. Depart to location; TBM; gas test. Shut in well. Rig up wireline equipment onto wellhead. Run in hole 1.75" Gauge Ring to HUD at 5358'WLD (5372'RKB), pull out of hole. Run in hole 1.85" gauge Ring and tag XN nipple at 5129'WLD (5143'RKB); Pull out of hole. Rig out wireline equipment from wellhead. Flow well back online. depart from location. Hand back work permit and generate report.
Forward Plan : |  | East Mereenie 38 / 39 / 41 - Drifts Runs.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-13
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 40
Type of operation | Drifts Runs
24 Hour summary | Obtain work permit. Depart to location; TBM; gas test. Shut in well. Rig up wireline equipment onto wellhead. Run in hole 1.75" Gauge Ring to HUD at 5358'WLD (5372'RKB), pull out of hole. Run in hole 1.85" gauge Ring and tag XN nipple at 5129'WLD (5143'RKB); Pull out of hole. Rig out wireline equipment from wellhead. Flow well back online. depart from location. Hand back work permit and generate report.
Forward plan | East Mereenie 38 / 39 / 41 - Drifts Runs.
Archive file name | east_mereenie_40_2008-05-13_drifts_runs_wl46.xls