## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-19
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Pull XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 34 |  | Assistant |  | Jonathan Musgrave
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FTHP | 427 | 393 | Serial and Type | 70574-1 | WMG EMR |  | 8168 /8169
Pcsg | 438 | 665 | Gas Detector | Dragger | Pipe Package
Icsg | 53 | 48 | Serial Number | ARWE-0438 | Flowprover
Scsg |  |  | Wellhead Recorder : Crystal |  | S/line Truck Km's |  | 6
[5 empty] | Crane Truck KM's |  | 24
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. R/up Wireline. Retrieved P-prong from PXN-plug body at XN-nipple @5127'WLD (5141'KB). Pull out of hole. Retrieved PXN-plug body with 2 x EMR from XN-nipple at 5130'WLD (5144'KB), pull out of hole. Open SSD at 4966'WLD (4980'KB) & SSD at 5106'WLD (5120'KB), pull out of hole. Open back SSD at 4966'WLD (4980'KB), pull out of hole. Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Service wireline tools, download EMR gauges and generate report.
Forward Plan : |  | East Mereenie 38 - Zone Isolation Test.
Time | Description
0600 | Attend morning meeting and obtain wellhead handover permit.
0650 | Depart from yard.
0710 | Arrive location; TBM & gas test (LEL=0%; OXY.=20.9%). CITHP=427psi; PCP=438psi.
0720 | Discarded 80' wire and re-knot rope socket.
Rig up wireline equipment onto wellhead.
0820 | RIH 2" SB and retrieved P-prong from PXN plug body at XN-nipple @ 5127'WLD (5141'KB), pull out of hole.
THP build up from 438 psi to 755 psi.
0900 | RIH 2" GS and retrieved PXN-plug body with EMR gauges from XN-nipple at 5130'WLD (5144'KB), pull out of hole.
THP build up from 755 psi to 813 psi after tool string pull out from hole.
On surface and disconnect EMR gauges, battery disconnect at 1001HRS.
1045 | RIH 2" B-shifting tool and Open SSD at 4966'WLD (4980'KB) & SSD at 5106'WLD (5120'KB), pull out of hole,
pin not sheared. THP=680; PCP=672psi.
1250 | RIH 2" B-shifting tool and close back SSD at 4966'WLD (4980'KB), pull out of hole, pin not sheared.
1330 | Rig down wireline equipment from wellhead and secured well. CITHP=670psi; Pcp=630psi; ICP=48psi.
1400 | Flow well to production line. FTHP=393psi; PCP=665psi; ISP=48psi.
1430 | Depart from location.
1450 | Arrive yard, fill up fuel and service wireline truck.
1600 | Service wireline tools; download and re-programme EMR.
1700 | Generate report.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18181'
Runs |  | 4 | Wire Cut | 80' | Balance |  | 18101'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-19
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Pull XN-plug w/EMR; Open SSD.
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 34 |  | Assistant |  | Jonathan Musgrave
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 427 | 393 | Serial and Type | 70574-1 | Crane |  | 8168 /8169
Pcsg | 438 | 665 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 53 | 48 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 6
|  |  | Toyota Km's | 0 | Truck Km's |  | 24
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. R/up Wireline. Retrieved P-prong from PXN-plug body at XN-nipple @5127'WLD (5141'KB). Pull out of hole. Retrieved PXN-plug body with 2 x EMR from XN-nipple at 5130'WLD (5144'KB), pull out of hole. Open SSD at 4966'WLD (4980'KB) & SSD at 5106'WLD (5120'KB), pull out of hole. Open back SSD at 4966'WLD (4980'KB), pull out of hole. Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Service wireline tools, download EMR gauges and generate report.
Forward Plan : |  | East Mereenie 38 - Zone Isolation Test.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-19
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 34
Type of operation | Pull XN-plug w/EMR; Open SSD.
24 Hour summary | Morning meeting. Depart to location, TBM; gas test. R/up Wireline. Retrieved P-prong from PXN-plug body at XN-nipple @5127'WLD (5141'KB). Pull out of hole. Retrieved PXN-plug body with 2 x EMR from XN-nipple at 5130'WLD (5144'KB), pull out of hole. Open SSD at 4966'WLD (4980'KB) & SSD at 5106'WLD (5120'KB), pull out of hole. Open back SSD at 4966'WLD (4980'KB), pull out of hole. Rig out wireline equipment from well head and flow well back to production line. Depart from location and back to yard. Service wireline tools, download EMR gauges and generate report.
Forward plan | East Mereenie 38 - Zone Isolation Test.
Archive file name | east_mereenie_34_2008-05-19_pull_xn-plug_w/emr;_open_ssd_wl46.xls