## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-18
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Close SSD
Customer Representative |  | Paul Michell |  | Wireline Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  |  |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
FTHP | 183 | 433 | Serial and Type | 70574-1 | WMG EMR |  | 8168 /8169
Pcsg | 455 | 438 | Gas Detector | Dragger | Pipe Package
Icsg | 73 | 73 | Serial Number | ARWE-0438 | Flowprover
Scsg |  |  | Wellhead Recorder : Crystal |  | S/line Truck Km's |  | 7
[5 empty] | Crane Truck KM's |  | 18
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. Shut in well and monitor for 2 HRS. THP build up from 183psi to 368 psi. R/up Wireline. Closed SSD at 5106'WLD (5120'KB); While pull out of hole after SSD closed, at 4150'WLD, Hydraulic oil return line to tank on wireline unit had disconnected from the clamp, resulting hydraulic oil spell on truck and at ground, losing power on winch. Unable to pull wire out of hole. Fill up hydraulic oil to tank and continue to pull wireline out from hole. Inject THP from PCP to 433 psi. Advise by production supervisor to stop operation. Rig down wireline equipment from wellhead and secured well. Clean up work area and wireline truck.
Forward Plan : |  | East Mereenie 40 - Zone Isolate Test -- Continue as per programme.
Time | Description
0600 | Attend morning meeting.
0630 | Depart from yard.
0730 | Arrive location; TBM & gas test (LEL=0%; OXY.=20.9%). Shut in well at 0720HRS.
Monitor for 2 HRS, THP build up from 83psi to 368psi.
0920 | Rig up wireline equipment onto wellhead and pressure tested against CITHP.
0950 | Run in hole 2" B-shifting tool and closed SSD at 5106'WLD (5120'KB); While pull out of hole after SSD closed,
at 4150'WLD, Hydraulic oil return line to tank on wireline unit has disconnected from the clamp, resulting hydraulic
oil spell on truck and on ground, no power on winch. Unable to pull wire out of hole.
1100 | Secure wire, call production operator for investigation work site.
1130 | Depart to workshop and load hydraulic oil, back to location.
Fill up hydraulic oil to tank and continue to pull wireline out from hole.
1220 | Inject THP from PCP to 433 psi.
1320 | Advise by production supervisor to stop operation and clean up work area and wireline truck.
1330 | Rig down wireline equipment from wellhead and secured well.
1410 | Depart from location.
1425 | Arrive workshop and clean up wireline truck.
1530 | Travel to EM40 and assist council personal to clean up work area.
1630 | Back to yard and generate report.
Wire Performance |  |  | Wire Size | 0.108" | Wire Type |  | stainless
Twist Test |  | Nil | Days in Service |  | Previous Balance |  | 18181'
Runs |  | 1 | Wire Cut | Nil | Balance |  | 18181'
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | Santos |  | DATE | 2008-05-18
|  |  | PROGRAM | Zone Isolation test.
Customer |  | Santos |  | Type of Operation |  | Close SSD
Customer Representative |  | Paul Michell |  | Operator |  | Lim Hiong Vui
Well Name |  | East Mereenie 40 |  | Assistant |  | Jonathan Musgrave
Formation |  | 0 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Vaetrix | Wireline Unit |  | 218
F / SI .THP | 183 | 433 | Serial and Type | 70574-1 | Crane |  | 8168 /8169
Pcsg | 455 | 438 | Gas Detector | Dragger | Downhole Gauges |  | 0
Icsg | 73 | 73 | Vaetrix | ARWE-0438 | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 7
|  |  | Toyota Km's | 0 | Truck Km's |  | 18
SEQUENCE OF EVENTS
24 Hr Summary : |  | Morning meeting. Depart to location, TBM; gas test. Shut in well and monitor for 2 HRS. THP build up from 183psi to 368 psi. R/up Wireline. Closed SSD at 5106'WLD (5120'KB); While pull out of hole after SSD closed, at 4150'WLD, Hydraulic oil return line to tank on wireline unit had disconnected from the clamp, resulting hydraulic oil spell on truck and at ground, losing power on winch. Unable to pull wire out of hole. Fill up hydraulic oil to tank and continue to pull wireline out from hole. Inject THP from PCP to 433 psi. Advise by production supervisor to stop operation. Rig down wireline equipment from wellhead and secured well. Clean up work area and wireline truck.
Forward Plan : |  | East Mereenie 40 - Zone Isolate Test -- Continue as per programme.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-05-18
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | East Mereenie 40
Type of operation | Close SSD
24 Hour summary | Morning meeting. Depart to location, TBM; gas test. Shut in well and monitor for 2 HRS. THP build up from 183psi to 368 psi. R/up Wireline. Closed SSD at 5106'WLD (5120'KB); While pull out of hole after SSD closed, at 4150'WLD, Hydraulic oil return line to tank on wireline unit had disconnected from the clamp, resulting hydraulic oil spell on truck and at ground, losing power on winch. Unable to pull wire out of hole. Fill up hydraulic oil to tank and continue to pull wireline out from hole. Inject THP from PCP to 433 psi. Advise by production supervisor to stop operation. Rig down wireline equipment from wellhead and secured well. Clean up work area and wireline truck.
Forward plan | East Mereenie 40 - Zone Isolate Test -- Continue as per programme.
Archive file name | east_mereenie_40_2008-05-18_close_ssd_wl46.xls