## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-09-17
|  |  | PROGRAM | Pressure Build up Survey
Customer |  | Santos |  | Type of Operation |  | PBU
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | East Mereenie 21 |  | Assistant |  | Troy Cartwright
Formation |  | Pacoota P3 Barefoot |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge |  | Wireline Unit |  | 207
F / SI .THP | 488 psi | 629 psi | Serial and Type |  | Crane |  | Unic 350
Pcsg | 497 psi | 500 psi | Gas Detector | Drager | Downhole Gauges |  | Weatherford
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers |  | 8169 / 8168
Scsg | 0 psi | 0 psi | Toyota | Hertz Rental | Truck |  | 196
|  |  | Toyota Km's | 25 kms | Truck Km's |  | 13 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Travel to location, rig up W/L. Run in hole 1.875" GS pulling tool & latch gauges in XN nipple @ 4616' KB, pull out of hole. Conducting gradient stops as per program. Rig down W/L. Return well to production.
Forward Plan : |  | Static Gradient Survey on East Mereenie 22
Time | Description
0600 | Toolbox meeting.
0700 | Permits.
0730 | Travel to EM 21.
0745 | Gas checks.
0750 | Rig up W/L.
0825 | Run in hole 1.875" GS pulling tool & latch gauges set in XN nipple @ 4616' KB.
0836 | Pull out of hole conducting gradient stops @ 4500', 4000', 3500', 3000', 2500', 2000', 1500', 1000', & 500', KB. .
0941 | 10 minutes in lubricator.
0951 | Depressure lubricator.
1000 | Disengage batteries.
1005 | Rig down W/L.
1015 | Return well to production
1030 | Depart lease for SGS yard.
1100 | Down load gauges & check data.
1130 | Reprogram gauges.
1300 | Travel to EM22
Note: Gauges engaged @ 1401 on 14/09/07 & Run in hole 1430 14/09/07, well flowed till 21:15 14/09/07 when it
was shut in for build up.
Wire Performance |  |  | Wire Size | .108" | Wire Type |  | Plough
Twist Test |  |  | Days in Service |  | Previous Balance
Runs |  |  | Wire Cut |  | Balance
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | 0 |  | DATE | 2007-09-17
|  |  | PROGRAM | Pressure Build up Survey
Customer |  | Santos |  | Type of Operation |  | PBU
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | East Mereenie 21 |  | Assistant |  | Troy Cartwright
Formation |  | Pacoota P3 Barefoot |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | 0 | Wireline Unit |  | 207
F / SI .THP | 488 psi | 629 psi | Serial and Type | 0 | Crane |  | Unic 350
Pcsg | 497 psi | 500 psi | Gas Detector | Drager | Downhole Gauges |  | Weatherford
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers |  | 8169 / 8168
Scsg | 0 psi | 0 psi | Toyota | Hertz Rental | Truck |  | 196
|  |  | Toyota Km's | 25 kms | Truck Km's |  | 13 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Travel to location, rig up W/L. Run in hole 1.875" GS pulling tool & latch gauges in XN nipple @ 4616' KB, pull out of hole. Conducting gradient stops as per program. Rig down W/L. Return well to production.
Forward Plan : |  | Static Gradient Survey on East Mereenie 22
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2007-09-17
Contractor | SGS
Rig/crew | WL 46
Well | East Mereenie 21
Type of operation | PBU
24 Hour summary | Travel to location, rig up W/L. Run in hole 1.875" GS pulling tool & latch gauges in XN nipple @ 4616' KB, pull out of hole. Conducting gradient stops as per program. Rig down W/L. Return well to production.
Forward plan | Static Gradient Survey on East Mereenie 22
Archive file name | east_mereenie_21_2007-09-17_pbu_wl_46.xls