## EDR2
COMPLETIONS - CBU
DAILY REPORT - ELECTRIC LINE
Date: | 2008-10-06 |  |  | 2 |  | Page 1 of 1
CONTRACTOR |  | WELL NAME | CREW |  | TYPE OF OPERATION
SGS Upstream Services |  | West Mereenie 14 | SGS CH1 |  | Slickline Drift
Cost Code
24 HOUR SUMMARY - |  | RIH 1.75" GC, Tag HUD @ 3992'kb, No problems encountered. POOH. ; RIH 1.75'x 20' Drift. Drift well down to 3960'kb, No problems encountered. POOH. ; -- Job Completed ; |  |  |  |  | 1 | á | enter 1 when job is completed | RIH 1.75" GC, Tag HUD @ 3992'kb, No problems encountered. POOH. ; RIH 1.75'x 20' Drift. Drift well down to 3960'kb, No problems encountered. POOH. ; -- Job Completed ;
(to 6am)
FORWARD PLAN - |  | East Mereenie 15. | [7 empty] | Job Completed
Job NOT Completed
TIME BREAKDOWN
TIME BREAKDOWN | DETAILS
6:00 | Santos morning safety meeting. | [6 empty] | á | enter 1 copy line to 24 hour summary
6:30 | Standby for Heat stress training. | [6 empty] | á | enter 1 copy line to 24 hour summary
7:00 | Attend Heat stress awareness training. | [6 empty] | á | enter 1 copy line to 24 hour summary
9:00 | Standby for Operator. | [6 empty] | á | enter 1 copy line to 24 hour summary
9:40 | Obtain Well handover and depart base for WM 14. | [6 empty] | á | enter 1 copy line to 24 hour summary
10:00 | Arrive location, conduct gas checks 0 LEL 20.9% Oxy. Hold toolbox talk. | [6 empty] | á | enter 1 copy line to 24 hour summary
10:10 | MIRU wireline unit, make up toolstring and pressure test PCE. | [6 empty] | á | enter 1 copy line to 24 hour summary
10:50 | RIH 1.75" GC, Tag HUD @ 3992'kb, No problems encountered. POOH. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
11:25 | OOH BO tools, make up 1.75"x 20' Drift. | [6 empty] | á | enter 1 copy line to 24 hour summary
11:45 | RIH 1.75'x 20' Drift. Drift well down to 3960'kb, No problems encountered. POOH. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
12:15 | OOH BO tools and clean. | [6 empty] | á | enter 1 copy line to 24 hour summary
12:45 | RDMO Wireline unit. | [6 empty] | á | enter 1 copy line to 24 hour summary
13:15 | Secure Lease and depart for EM 15. | [6 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
|  |  |  | Supervisor: | R. Turner
Santos
Copy Text to 24hr. Summary

## Perforating Activity Report
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report: | PAGE 2 OF 2
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## Perforating Activity Report Pg2
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report:
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-10-06
Contractor | SGS Upstream Services
Rig/crew | SGS CH1
Well | West Mereenie 14
Type of operation | Slickline Drift
24 Hour summary | RIH 1.75" GC, Tag HUD @ 3992'kb, No problems encountered. POOH. ; RIH 1.75'x 20' Drift. Drift well down to 3960'kb, No problems encountered. POOH. ; -- Job Completed ;
Forward plan | East Mereenie 15.
Archive file name | west_mereenie_14_2008-10-06_slickline_drift_sgs_ch1.xls