## EDR2
COMPLETIONS - CBU
DAILY REPORT - ELECTRIC LINE
Date: | 2008-10-06 |  |  | 2 |  | Page 1 of 1
CONTRACTOR |  | WELL NAME | CREW |  | TYPE OF OPERATION
SGS Upstream Services |  | East Mereenie 15 | SGS CH1 |  | Slickline SGS
Cost Code
24 HOUR SUMMARY - |  | Open Well and conduct Static gradient survey with station stops @ Lub, 4713', 4500', 4000', 3000', 2000', 1000', Lub. ; -- Job Completed ; |  |  |  |  | 1 | á | enter 1 when job is completed | Open Well and conduct Static gradient survey with station stops @ Lub, 4713', 4500', 4000', 3000', 2000', 1000', Lub. ; -- Job Completed ;
(to 6am)
FORWARD PLAN - |  | EM 2 | [7 empty] | Job Completed
Job NOT Completed
TIME BREAKDOWN
TIME | DETAILS
13:15 | Secure and depart from WM 14. | [6 empty] | á | enter 1 copy line to 24 hour summary
14:00 | Arrive EM 15, conduct gas checks 0 LEL 20.9% Oxy. Hold toolbox talk. | [6 empty] | á | enter 1 copy line to 24 hour summary
14:10 | MIRU Wireline unit and make up 2 x memory Gauges. | [6 empty] | á | enter 1 copy line to 24 hour summary
14:40 | Open Well and conduct Static gradient survey with station stops @ Lub, 4713', 4500', 4000', 3000', 2000', 1000', Lub. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
17:15 | OOH BO Gauges and Disconnect. | [6 empty] | á | enter 1 copy line to 24 hour summary
17:20 | RDMO Wireline unit. | [6 empty] | á | enter 1 copy line to 24 hour summary
17:45 | Secure lease and depart for base. | [6 empty] | á | enter 1 copy line to 24 hour summary
18:15 | Arrive and Generate daily reports. | [6 empty] | á | enter 1 copy line to 24 hour summary
19:30 | End of day. | [6 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
| Time Well Open | 0:15 | [5 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
| Time Well Shut in | 0:17 | [5 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
| Top Gauge | 8144 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Battery | B17467 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Time Connected | 0:14 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Time Disconnected | 0:17 | [5 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
| Bottom Gauge | 8147 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Battery | D18003 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Time Connected | 0:14 | [5 empty] | á | enter 1 copy line to 24 hour summary
| Time Disconnected | 0:17 | [5 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
|  |  |  | Supervisor: | R. Turner
Santos
Copy Text to 24hr. Summary

## Perforating Activity Report
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report: | PAGE 2 OF 2
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## Perforating Activity Report Pg2
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report:
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-10-06
Contractor | SGS Upstream Services
Rig/crew | SGS CH1
Well | East Mereenie 15
Type of operation | Slickline SGS
24 Hour summary | Open Well and conduct Static gradient survey with station stops @ Lub, 4713', 4500', 4000', 3000', 2000', 1000', Lub. ; -- Job Completed ;
Forward plan | EM 2
Archive file name | east_mereenie_15_2008-10-06_slickline_sgs_sgs_ch1.xls