## EDR2
COMPLETIONS - CBU
DAILY REPORT - ELECTRIC LINE
Date: | 2008-10-05 |  |  | 2 |  | Page 1 of 1
CONTRACTOR |  | WELL NAME | CREW |  | TYPE OF OPERATION
SGS Upstream Services |  | East Mereenie 15 | SGS CH1 |  | Slickline Drift
Cost Code
24 HOUR SUMMARY - |  | RIH 1.75" GC. Tag HUD @ 4758'kb. No problems encountered. POOH. ; RIH 2.34" GC, Tag XN nipple @ 4619'kb. No problems encountered. POOH. ; RIH 1.75"x 20' Drift. Drift well down to 4750'kb. No problems encountered. POOH. ; -- Job Completed ; |  |  |  |  | 1 | á | enter 1 when job is completed | RIH 1.75" GC. Tag HUD @ 4758'kb. No problems encountered. POOH. ; RIH 2.34" GC, Tag XN nipple @ 4619'kb. No problems encountered. POOH. ; RIH 1.75"x 20' Drift. Drift well down to 4750'kb. No problems encountered. POOH. ; -- Job Completed ;
(to 6am)
FORWARD PLAN - |  | West Mereenie 12. | [7 empty] | Job Completed
Job NOT Completed
TIME BREAKDOWN
TIME | DETAILS
6:00 | Santos Morning safety meeting. | [6 empty] | á | enter 1 copy line to 24 hour summary
6:30 | Prepare tools and equipment. | [6 empty] | á | enter 1 copy line to 24 hour summary
7:00 | Standby for Operator. | [6 empty] | á | enter 1 copy line to 24 hour summary
8:30 | Depart base for EM 15. | [6 empty] | á | enter 1 copy line to 24 hour summary
9:00 | Arrive location, conduct gas checks 0 LEL 20.9% Oxy. Hold toolbox talk. | [6 empty] | á | enter 1 copy line to 24 hour summary
9:10 | MIRU wireline unit, make up toolstring and pressure test PCE. | [6 empty] | á | enter 1 copy line to 24 hour summary
9:35 | RIH 1.75" GC. Tag HUD @ 4758'kb. No problems encountered. POOH. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
10:05 | OOH BO tools, Make up 2.34" GC. | [6 empty] | á | enter 1 copy line to 24 hour summary
10:10 | RIH 2.34" GC, Tag XN nipple @ 4619'kb. No problems encountered. POOH. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
10:40 | OOH BO tools, Make up 1.75"x 20' drift. | [6 empty] | á | enter 1 copy line to 24 hour summary
11:00 | RIH 1.75"x 20' Drift. Drift well down to 4750'kb. No problems encountered. POOH. | [5 empty] | 1 | á | enter 1 copy line to 24 hour summary
11:40 | OOH BO tools and clean. | [6 empty] | á | enter 1 copy line to 24 hour summary
12:00 | RDMO Wireline unit. | [6 empty] | á | enter 1 copy line to 24 hour summary
12:30 | Secure lease and depart for base. | [6 empty] | á | enter 1 copy line to 24 hour summary
13:10 | Standby for Santos Rep for further instruction. | [6 empty] | á | enter 1 copy line to 24 hour summary
14:30 | Depart for West Mereenie 12. | [6 empty] | á | enter 1 copy line to 24 hour summary
14:50 | Arrive location, conduct gas checks 0 LEL 20.9% Oxy. Hold toolbox talk. | [6 empty] | á | enter 1 copy line to 24 hour summary
15:00 | Unable to Rig up as Wellhead Master valves are Passing. | [6 empty] | á | enter 1 copy line to 24 hour summary
15:15 | Depart WM 12 for base. | [6 empty] | á | enter 1 copy line to 24 hour summary
15:35 | Arrive base, Continue inspection of E-Line equipment. | [6 empty] | á | enter 1 copy line to 24 hour summary
18:00 | Generate daily report. | [6 empty] | á | enter 1 copy line to 24 hour summary
18:30 | End of Day. | [6 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
[8 empty] | á | enter 1 copy line to 24 hour summary
|  |  |  | Supervisor: | R. Turner
Santos
Copy Text to 24hr. Summary

## Perforating Activity Report
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report: | PAGE 2 OF 2
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## Perforating Activity Report Pg2
Santos | [10 empty] | CBU COMPLETIONS DAILY REPORT
PERFORATING ACTIVITY FORM
|  |  | Well: |  |  |  |  | Date: |  |  |  | MRU Date: |  |  |  | Report:
|  |  | Engineer: |  |  |  |  | Lead Operator: |  |  |  | R/D Date: | [7 empty] | SGS
[5 empty] | GUN DETAILS | [7 empty] | TIME |  |  |  |  | DRAWDOWN/BUILD-UP DATA
(pressure @ 5 min intervals)
Run | Perforating Interval (ft RTKB) | Sand # | Gun Size | Charge Type | Shots/ft | M | Explosive Weight | Measured Gun Length (ft) | CCL to Top Shot (ft) | CCL Shot Depth (ft RTKB) | RIH Gun | Fluid Level (ft RTKB) | Open Well | Fire Gun / SIW | POOH | Gun @ Surface | Time (hh:mm) | Pressure (PSI) | Choke | Comments | Gun Fired Y/N
| Depart Camp |  |  |  | Daily Cost |  |  | Safety Meeting Held: |  |  | REMARKS:
| Arrive Location: |  |  |  | Cum. Cost
Depart Location
Return Camp

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-10-05
Contractor | SGS Upstream Services
Rig/crew | SGS CH1
Well | East Mereenie 15
Type of operation | Slickline Drift
24 Hour summary | RIH 1.75" GC. Tag HUD @ 4758'kb. No problems encountered. POOH. ; RIH 2.34" GC, Tag XN nipple @ 4619'kb. No problems encountered. POOH. ; RIH 1.75"x 20' Drift. Drift well down to 4750'kb. No problems encountered. POOH. ; -- Job Completed ;
Forward plan | West Mereenie 12.
Archive file name | east_mereenie_15_2008-10-05_slickline_drift_sgs_ch1.xls