## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-09-13
|  |  | PROGRAM | Static gradient surveys
Customer |  | Santos |  | Type of Operation |  | SGS
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | East Mereenie 16 |  | Assistant |  | Troy Cartwright
Formation |  | Pacoota P3 |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge |  | Wireline Unit |  | 207
F / SI .THP | 605 psi | 606 psi | Serial and Type |  | Crane |  | Unic 350
Pcsg | 19 psi | 19 psi | Gas Detector | Drager | Downhole Gauges |  | Weatherford
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers |  | 8169 / 8168
Scsg | 45 psi | 45 psi | Toyota | Hertz Rental | Truck |  | 196
|  |  | Toyota Km's | 30 kms | Truck Km's |  | 15 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Travel to location, rig up W/L. Run in hole 1.75" GR & tag PBTD @ 4654' KB, Pull out of hole. Run in hole 2.34" GR & tag nipple @ 4423' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L.
Forward Plan : |  | Static Gradient Survey on East Mereenie 35
Time | Description
0600 | Toolbox meeting.
0730 | Liase with Santos Reps.
1000 | Travel to EM16.
1030 | Rig up W/L.
1100 | Stand by for stabilisation.
1240 | Return to well site.
1310 | Run in hole 1.75" GR & tag PBTD @ 4654' KB.
1320 | Pull out of hole.
1330 | Run in hole 2.34" GR & tag nipple @ 4423' KB.
1340 | Pull out of hole
1341 | Engage batteries.
1355 | Pressure up lubricator.
1405 | Run in hole tandem memory gauges.
1420 | On depth @ 4616' KB.
1430 | Pull out of hole conducting stops @ 4500', 4250', 4000', 3500', 3000', 2500', 2000', 1500' & 1000', KB
1528 | At surface 10 minutes in lubricator.
1538 | Depressure lubricator.
1557 | Disengage batteries.
1600 | Rig down W/L.
1615 | Return well to production
1620 | Travel EM16 to SGS yard.
1640 | Generate reports.
1700 | Down load gauges & reprogram gauges.
1800 | End of day.
Wire Performance |  |  | Wire Size | .108" | Wire Type |  | Plough
Twist Test |  |  | Days in Service |  | Previous Balance
Runs |  |  | Wire Cut |  | Balance
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | 0 |  | DATE | 2007-09-13
|  |  | PROGRAM | Static gradient surveys
Customer |  | Santos |  | Type of Operation |  | SGS
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | East Mereenie 16 |  | Assistant |  | Troy Cartwright
Formation |  | Pacoota P3 |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | 0 | Wireline Unit |  | 207
F / SI .THP | 605 psi | 606 psi | Serial and Type | 0 | Crane |  | Unic 350
Pcsg | 19 psi | 19 psi | Gas Detector | Drager | Downhole Gauges |  | Weatherford
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers |  | 8169 / 8168
Scsg | 45 psi | 45 psi | Toyota | Hertz Rental | Truck |  | 196
|  |  | Toyota Km's | 30 kms | Truck Km's |  | 15 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Travel to location, rig up W/L. Run in hole 1.75" GR & tag PBTD @ 4654' KB, Pull out of hole. Run in hole 2.34" GR & tag nipple @ 4423' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L.
Forward Plan : |  | Static Gradient Survey on East Mereenie 35
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2007-09-13
Contractor | SGS
Rig/crew | WL 46
Well | East Mereenie 16
Type of operation | SGS
24 Hour summary | Travel to location, rig up W/L. Run in hole 1.75" GR & tag PBTD @ 4654' KB, Pull out of hole. Run in hole 2.34" GR & tag nipple @ 4423' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L.
Forward plan | Static Gradient Survey on East Mereenie 35
Archive file name | east_mereenie_16_2007-09-13_sgs_wl_46.xls