## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2007-10-01
|  |  | PROGRAM | SGS
Customer |  | Santos |  | Type of Operation |  | SGS
Customer Representative |  | Paul Michell |  | Operator |  | Mark Longstaff
Well Name |  | East Mereenie 17. |  | Assistant |  | Shane Cox
Formation |  | Pacoota |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge |  | Wireline Unit |  | 207
F / SI .THP | 739 | 749 | Serial and Type |  | Crane |  | Unic 350
Pcsg | N/A | N/A | Gas Detector | Drager | Downhole Gauges
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers
Scsg | N/A | N/A | Toyota |  | Truck |  | 196
|  |  | Toyota Km's |  | Truck Km's
SEQUENCE OF EVENTS
24 Hr Summary : |  | Attend Santos Morning Meeting. Standby for EM 17 SGS. Prepare equipment for de-mobe. Conduct static gradient EM 17.
Forward Plan : |  | Demobilise pending weatherford completion of WM-15 perforating job.
Time | Description
06:00 | Attend Santos morning meeting.
06:45 | Prepare wireline equipment and workshop for demobilisation.
12:15 | Depart base.
12:40 | Arrive location. TBM. LEL 0.0%. Oxy 20.9%. SITHP 739 psi.
12:45 | Rig up slickline.
13:05 | Run in hole 1.84" gauge cutter and tag 1.875" XN nipple @ 4602' wl. (4617' KB). Pooh.
13:30 | Run in hole 1.75" gauge cutter and tag TD @ 4667' wl. (4672' KB). Pooh.
Note: Both gauge cutters and toolstring covered in frac sand.
14:07 | Connect gauge batteries.
14:18 | Pressure up lubricator.
14:29 | Run in hole tandem EMR gauges and conduct gradient survey with station stops as follows:
| Depth WL |  | Arrive |  | Depart |  | Stay
| Lub |  | 14:18 |  | 14:29 |  | 10
| 4640 |  | 14:50 |  | 15:00 |  | 5
| 4485 |  | 15:02 |  | 15:07 |  | 5
| 4235 |  | 15:09 |  | 15:14 |  | 5
| 3985 |  | 15:15 |  | 15:20 |  | 5
| 3485 |  | 15:23 |  | 15:28 |  | 5
| 2985 |  | 15:30 |  | 15:35 |  | 5
| 2485 |  | 15:37 |  | 15:42 |  | 5
| 1985 |  | 15:45 |  | 15:50 |  | 5
| 1485 |  | 15:52 |  | 15:57 |  | 5
| 985 |  | 15:59 |  | 16:04 |  | 5
| Lub |  | 16:09 |  | 16:20 |  | 10
Wire Performance |  |  | Wire Size | .108" | Wire Type |  | Plough steel
Twist Test |  |  | Days in Service | 95 | Previous Balance |  | 18717
Runs |  | 3 | Wire Cut | 0 | Balance |  | 18717
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | 0 |  | DATE | 2007-10-01
|  |  | PROGRAM | SGS
Customer |  | Santos |  | Type of Operation |  | SGS
Customer Representative |  | Paul Michell |  | Operator |  | Mark Longstaff
Well Name |  | East Mereenie 17. |  | Assistant |  | Shane Cox
Formation |  | Pacoota |  | Crew |  | WL 46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | 0 | Wireline Unit |  | 207
F / SI .THP | 739 | 749 | Serial and Type | 0 | Crane |  | Unic 350
Pcsg | 0 | 0 | Gas Detector | Drager | Downhole Gauges |  | 0
Icsg | N/A | N/A | Vaetrix | Yes | Serial Numbers |  | 0
Scsg | 0 | 0 | Toyota | 0 | Truck |  | 196
|  |  | Toyota Km's | 0 | Truck Km's |  | 32
SEQUENCE OF EVENTS
24 Hr Summary : |  | Attend Santos Morning Meeting. Standby for EM 17 SGS. Prepare equipment for de-mobe. Conduct static gradient EM 17.
Forward Plan : |  | Demobilise pending weatherford completion of WM-15 perforating job.
Time | Description
16:20 | Depressure lubricator. SITHP 749 psi.
16:36 | Disconnect batteries. Rig down slickline.
16:38 | Well on line.
17:00 | Depart location.
17:30 | Arrive base. Generate report. Download gauges. Data good.
18:00 | End of day
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2007-10-01
Contractor | SGS
Rig/crew | WL 46
Well | East Mereenie 17.
Type of operation | SGS
24 Hour summary | Attend Santos Morning Meeting. Standby for EM 17 SGS. Prepare equipment for de-mobe. Conduct static gradient EM 17.
Forward plan | Demobilise pending weatherford completion of WM-15 perforating job.
Archive file name | east_mereenie_17_2007-10-01_sgs_wl_46.xls