## Summary
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 1
|  |  | CLIENT REF |  |  | DATE | 2008-06-14
|  |  | PROGRAM | Static gradient survey
Customer |  | Santos |  | Type of Operation |  | Static gradient survey
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | West Mereenie 4 |  | Assistant |  | Caspar D'huij
Formation |  | Pacoota P3 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Wireline Unit |  | 218
F / SI .THP | 66 psi | 65 psi | Serial and Type | 795413 | Crane |  | Unic 370
Pcsg | 120 psi | 124 psi | Gas Detector | Drager | Downhole Gauges |  | weatherford
Icsg | N/A | N/A | Vaetrix | N/A | Serial Numbers |  | 8168 / 8169
Scsg | 23 psi | 23 psi | Toyota | Crane truck. | Truck |  | 212
|  |  | Toyota Km's | 35 kms | Truck Km's |  | 35 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Attend morning meeting. Complete work permit. Prepare equipment. Travel to location & conduct gas checks. Rig up W/L. Run in hole 1.75" GR & tag PBTD @ 5016' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L. Down load gauges & check data OK. Hand well back to production. Generate reports.
Forward Plan : |  | East Mereenie 40 zone change.
Time | Description
0600 | Attend morning meeting.
0645 | Prepare equipment.
0700 | Complete work permit.
0730 | Travel to well site.
0800 | Arrive location & conduct gas checks.
0810 | Rig up W/L .
0845 | Run in hole 1.75" GR & tag PBTD @ 5016' KB.
0905 | Pull out of hole.
0905 | Engage batteries
1140 | Run in hole gauges.
1212 | On depth @ 4929' KB . Lost weight & adjusted hang depth.
1222 | Pull out of hole conducting stops @ 4500', 4000', 3500', 3000', 2500', 2000', 1500', 1000', & 500' KB.
1333 | At surface 5 minutes.
1348 | Disengage batteries.
1500 | Rig down W/L.
1520 | Depart lease for office.
1545 | Arrive SGS yard & down load gauges.
1600 | Check data OK.
1615 | Hand well back to production.
1730 | Generate reports.
1800 | End of day.
Wire Performance |  |  | Wire Size |  | Wire Type
Twist Test |  |  | Days in Service |  | Previous Balance
Runs |  |  | Wire Cut |  | Balance
CUSTOMER REPRESENTATIVE SIGNATURE

## Page 2
D A I L Y A C T I V I T Y / C H A R G E S R E P O R T
[6 empty] | PAGE | 2
|  |  | CLIENT REF | 0 |  | DATE | 2008-06-14
|  |  | PROGRAM | Static gradient survey
Customer |  | Santos |  | Type of Operation |  | Static gradient survey
Customer Representative |  | Paul Michell |  | Operator |  | Paul Hahn
Well Name |  | West Mereenie 4 |  | Assistant |  | Caspar D'huij
Formation |  | Pacoota P3 |  | Crew |  | WL46
Well Details :- |  |  | SGS Equipment Details:-
Pressures | Start | Finish | Pressure Gauge | Crystal | Wireline Unit |  | 218
F / SI .THP | 66 psi | 65 psi | Serial and Type | 795413 | Crane |  | Unic 370
Pcsg | 120 psi | 124 psi | Gas Detector | Drager | Downhole Gauges |  | weatherford
Icsg | N/A | N/A | Vaetrix | N/A | Serial Numbers |  | 8168 / 8169
Scsg | 23 psi | 23 psi | Toyota | Crane truck. | Truck |  | 212
|  |  | Toyota Km's | 35 kms | Truck Km's |  | 35 kms
SEQUENCE OF EVENTS
24 Hr Summary : |  | Attend morning meeting. Complete work permit. Prepare equipment. Travel to location & conduct gas checks. Rig up W/L. Run in hole 1.75" GR & tag PBTD @ 5016' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L. Down load gauges & check data OK. Hand well back to production. Generate reports.
Forward Plan : |  | East Mereenie 40 zone change.
Time | Description
CUSTOMER REPRESENTATIVE SIGNATURE

## PRISM
Santos | PRISM control information | Rev 1.0
Date | 2008-06-14
Contractor | SGS Upstream Services
Rig/crew | WL46
Well | West Mereenie 4
Type of operation | Static gradient survey
24 Hour summary | Attend morning meeting. Complete work permit. Prepare equipment. Travel to location & conduct gas checks. Rig up W/L. Run in hole 1.75" GR & tag PBTD @ 5016' KB. Pull out of hole. Run in hole tandem memory gauges & conduct survey as per program. Pull out of hole. Rig down W/L. Down load gauges & check data OK. Hand well back to production. Generate reports.
Forward plan | East Mereenie 40 zone change.
Archive file name | west_mereenie_4_2008-06-14_static_gradient_survey_wl46.xls