PROJECT; P2023121. CLIENT; ADROIT. PROJECT AREA; P2023121. SUPERVISOR; LM. OPERATORS; TB. SURVEY SIZE; 941. VEHICLES; 1GRZ014.

Production Table

| DATE | MOB STANDBY % | SURVEY % | 41081 FIELD | 41081 REPEAT | 41081 %REPEAT | FIELD TOTAL | REPEAT TOTAL | SURVEY TOTAL | SURVEY REMAIN | SURVEY REPEAT | SURVEY %REPEAT | SURVEY % COMPLETE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11/11/2023 | 95% | 5% | 4 | 1 | 25.00% | 4 | 1 | 4 | 937 | 1 | 25.00% | 0.43% |
| 12/11/2023 | 0% | 100% | 70 | 3 | 4.29% | 70 | 3 | 74 | 867 | 4 | 5.41% | 7.86% |
| 13/11/2023 | 0% | 100% | 72 | 2 | 2.78% | 72 | 2 | 146 | 795 | 6 | 4.11% | 15.52% |
| 14/11/2023 | 0% | 100% | 68 | 3 | 4.41% | 68 | 3 | 214 | 727 | 9 | 4.21% | 22.74% |
| 15/11/2023 | 0% | 100% | 52 | 2 | 3.85% | 52 | 2 | 266 | 675 | 11 | 4.14% | 28.27% |
| 16/11/2023 | 0% | 100% | 42 | 2 | 4.76% | 42 | 2 | 308 | 633 | 13 | 4.22% | 32.73% |
| 17/11/2023 | 0% | 100% | 57 | 2 | 3.51% | 57 | 2 | 365 | 576 | 15 | 4.11% | 38.79% |
| 18/11/2023 | 0% | 100% | 31 | 0 | 0.00% | 31 | 0 | 396 | 545 | 15 | 3.79% | 42.08% |
| 19/11/2023 | 0% | 100% | 62 | 2 | 3.23% | 62 | 2 | 458 | 483 | 17 | 3.71% | 48.67% |
| 20/11/2023 | 0% | 100% | 60 | 2 | 3.33% | 60 | 2 | 518 | 423 | 19 | 3.67% | 55.05% |
| 21/11/2023 | 0% | 100% | 60 | 2 | 3.33% | 60 | 2 | 578 | 363 | 21 | 3.63% | 61.42% |
| 22/11/2023 | 0% | 100% | 52 | 2 | 3.85% | 52 | 2 | 630 | 311 | 23 | 3.65% | 66.95% |
| 23/11/2023 | 0% | 100% | 29 | 1 | 3.45% | 29 | 1 | 659 | 282 | 24 | 3.64% | 70.03% |
| 24/11/2023 | 0% | 100% | 32 | 1 | 3.13% | 32 | 1 | 691 | 250 | 25 | 3.62% | 73.43% |
| 25/11/2023 | 50% | 50% | 13 | 1 | 7.69% | 13 | 1 | 704 | 237 | 26 | 3.69% | 74.81% |
| 30/11/2023 | 0% | 60% | 28 | 1 | 3.57% | 28 | 1 | 732 | 209 | 27 | 3.69% | 77.79% |
| 01/12/2023 | 0% | 100% | 54 | 2 | 3.70% | 54 | 2 | 786 | 155 | 29 | 3.69% | 83.53% |
| 02/12/2023 | 0% | 100% | 54 | 3 | 5.56% | 54 | 3 | 840 | 101 | 32 | 3.81% | 89.27% |
| 03/12/2023 | 0% | 100% | 46 | 2 | 4.35% | 46 | 2 | 886 | 55 | 34 | 3.84% | 94.16% |
| 04/12/2023 | 0% | 100% | 34 | 0 | 0.00% | 34 | 0 | 920 | 21 | 34 | 3.70% | 97.77% |
| 05/12/2023 | 0% | 100% | 21 | 0 | 0.00% | 21 | 0 | 941 | 0 | 34 | 3.61% | 100.00% |
| 06/12/2023 | 100% | 0% | 0 | 0 | 0.00% | 0 | 0 | 941 | 0 | 34 | 3.61% | 100.00% |

Supervisor Comments:

| DATE | COMMENT |
| --- | --- |
| 11/11/2023 | MOB Mobilised from Daly Waters to site. Tested control station and equipment by collecting four stations and one repeat at the end of the day. |
| 12/11/2023 | Overcast day, not too hot. Difficult road to navigate heading south with the UTV and trailer due to many wash outs and couple downed trees. Terrain in south easy but many detours required to navigate around creeks and some areas very muddy. |
| 13/11/2023 | Mostly clear day, slightly hotter temperature. Easy terrain in the morning with slightly more hills and rocky terrain in the afternoon. A lot of detours required in the east for plethora of creeks and bodies of water in area. |
| 14/11/2023 | Began day in the southwest, terrain got progressively more difficult the further west we travelled with hills, valleys and large rocks. River sized creeks blocked access to stations 1126 and 1147. |
| 15/11/2023 | Difficult terrain today east and west, a lot of steep hills with creeks running through valleys and rocks/boulders blocking most ways causing delays. |
| 16/11/2023 | We had tough terrain all day, very steep mountain faces causing large detours and even the flat parts today were covered in very large rocks making travel speed very slow. |
| 17/11/2023 | Large and steep hills in the morning, flatter terrain in the afternoon but had a lot of creeks to find our way through creating large detours. |
| 18/11/2023 | Finished the last of the big hills today, had a tyre valve stem break on our UTV today at station 1320, had to turn around back to road to repair and continue survey after. |
| 19/11/2023 | Easier terrain today, a lot of large rivers and creeks to detour around in the west caused delays. Parked trailer and UTV further north near main highway as south section almost complete. |
| 20/11/2023 | Mostly flat terrain today with large amount of creek crossings. Rain last night created muddy terrain in spots. |
| 21/11/2023 | Overcast all day, storm began rolling in around 2pm. Mostly flat terrain, last night caused creek/river crossing to be a little more challenging to find a dry crossing but smooth day today. |
| 22/11/2023 | Many creek crossings in the west, becoming increasingly more challenging with nightly rain recently, large hills continue in the east. |
| 23/11/2023 | UTV sustained damage to the transmission housing this morning at 8am, not able to drive UTV, had to walk all stations from 1655 onwards. |
| 24/11/2023 | Walked all stations today, hot and humid day, sunny in the morning and cloud coverage after 11am, mostly flat terrain today. |
| 25/11/2023 | GRAV TIE Walked all stations today, clear in the morning and very humid day. Performed gravity tie in the afternoon. Will be collecting new UTV and flying new employee in to finish surveying remaining points. |
| 30/11/2023 | Towed broken down UTV off grid and replaced with new in the morning. Surveyed during the afternoon in the east, hills and creeks to navigate through the day. |
| 01/12/2023 | We completed the, hard to access, stations upon the mountain areas this morning, moving north tomorrow to the flatter areas. Terrain was very rocky this hot conditions 40+. |
| 02/12/2023 | Completed the north eastern grid today, very hot conditions. A few creeks and rivers that weren't on the map needed crossing terrain was rocky with some flat loops. |
| 03/12/2023 | We tried to survey the northwest section of the grid, unable to access due to fences and large rivers on routes taken today. Surveyed the east of the large river in middle of grid near golf course. |
| 04/12/2023 | Completed all stations east of previously mentioned river and south of highway. We followed a river to find a crossing and no ways to cross found by buggy or by foot. To access northwest section of the grid a key will be required to unlock the gate between stations 1772 and 1773. If the key cannot be sourced will have to walk rest of stations remaining. |
| 05/12/2023 | Walked all stations today, were told after first loop completed that we were trespassing and were not allowed back onto property for remaining survey points. We were standby for 75% of day. Told to leave remaining points and pack up base station. |
| 06/12/2023 | DEMOB Crew demobilised from site. |

| FIELD | MEAN | SD | MINIMUM | MAXIMUM |
| --- | --- | --- | --- | --- |
| DIFFEASTM | -0.125 | 0.528 | -1.458 | 1.069 |
| DIFFNORTHM | -0.029 | 0.853 | -3.601 | 1.395 |
| DIFFHTM | 0.002 | 0.016 | -0.038 | 0.035 |
| DIFFOBSGMGAL | 0.009 | 0.018 | -0.020 | 0.038 |
| DIFFOBSGGU | 0.090 | 0.184 | -0.200 | 0.380 |