PROJECT; P2017098. CLIENT; Cameco. PROJECT AREA; Such Wow survey area 1. SUPERVISORS; Cameron Hoogendyk. OPERATORS; Cameron Hoogendyk, Ryan Hoogendyk. SURVEY SIZE; 1800. VEHICLES; Hire Car S670BFT.

Production Table

| DATE | MOB STANDBY % | SURVEY % | 40803 FIELD | 40803 REPEAT | 40803 %REPEAT | FIELD TOTAL | REPEAT TOTAL | SURVEY TOTAL | SURVEY REMAIN | SURVEY REPEAT | SURVEY %REPEAT | SURVEY % COMPLETE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10/08/2017 | 100% | 00% | 0 | 0 | 0.00% | 0 | 0 | 0 | 1800 | 0 | 0.00% | 0.00% |
| 11/08/2017 | 50% | 50% | 65 | 1 | 1.54% | 65 | 1 | 65 | 1735 | 1 | 1.54% | 3.61% |
| 12/08/2017 | 0% | 100% | 121 | 2 | 1.65% | 121 | 2 | 186 | 1614 | 3 | 1.61% | 10.33% |
| 13/08/2017 | 0% | 100% | 126 | 2 | 1.59% | 126 | 2 | 312 | 1488 | 5 | 1.60% | 17.33% |
| 14/08/2017 | 0% | 100% | 137 | 3 | 2.19% | 137 | 3 | 449 | 1351 | 8 | 1.78% | 24.94% |
| 15/08/2017 | 0% | 100% | 108 | 2 | 1.85% | 108 | 2 | 557 | 1243 | 10 | 1.80% | 30.94% |
| 16/08/2017 | 0% | 100% | 140 | 3 | 2.14% | 140 | 3 | 697 | 1103 | 13 | 1.87% | 38.72% |
| 17/08/2017 | 0% | 100% | 121 | 2 | 1.65% | 121 | 2 | 818 | 982 | 15 | 1.83% | 45.44% |
| 18/08/2017 | 0% | 100% | 110 | 2 | 1.82% | 110 | 2 | 928 | 872 | 17 | 1.83% | 51.56% |
| 19/08/2017 | 0% | 100% | 0 | 0 | 0.00% | 0 | 0 | 928 | 872 | 17 | 1.83% | 51.56% |
| 20/08/2017 | 0% | 100% | 113 | 3 | 2.65% | 113 | 3 | 1041 | 759 | 20 | 1.92% | 57.83% |
| 21/08/2017 | 0% | 100% | 138 | 3 | 2.17% | 138 | 3 | 1179 | 621 | 23 | 1.95% | 65.50% |
| 22/08/2017 | 0% | 100% | 124 | 3 | 2.42% | 124 | 3 | 1303 | 497 | 26 | 2.00% | 72.39% |
| 23/08/2017 | 0% | 100% | 156 | 2 | 1.28% | 156 | 2 | 1459 | 341 | 28 | 1.92% | 81.06% |
| 24/08/2017 | 0% | 100% | 117 | 1 | 0.85% | 117 | 1 | 1576 | 224 | 29 | 1.84% | 87.56% |
| 25/08/2017 | 0% | 100% | 82 | 2 | 2.44% | 82 | 2 | 1658 | 142 | 31 | 1.87% | 92.11% |
| 26/08/2017 | 0% | 100% | 95 | 4 | 4.21% | 95 | 4 | 1753 | 47 | 35 | 2.00% | 97.39% |
| 27/08/2017 | 0% | 100% | 47 | 3 | 6.38% | 47 | 3 | 1800 | 0 | 38 | 2.11% | 100.00% |
| 28/08/2017 | 100% | 0% | 0 | 0 | 0.00% | 0 | 0 | 1800 | 0 | 38 | 2.11% | 100.00% |

Supervisor Comments:

| DATE | COMMENT |
| --- | --- |
| 10/08/2017 | Crew departed Perth early morning and flew to Darwin. Crew picked up hire car and some supplies and then drove to the King River Camp arriving at 9pm. |
| 11/08/2017 | Crew attended morning meeting and induction then located existing gravity base 201102000001 ('Telstra Tower'). Damien escorted the crew out to the grid where they setup a new GNSS base at an old drill pad. Crew then started surveying in the northern part of the grid encountering rocky terrain and patches of thick trees. |
| 12/08/2017 | Crew continued surveying today, working south through the grid to the southern-most lines then looping back to the north. Due to the distance crew was unable to finish loop and deadwalked 2.7km back to the vehicle. |
| 13/08/2017 | Crew continued surveying in the northern part of the grid. Sunday weekly toolbox for both Cameco and Atlas were conducted in evening. |
| 14/08/2017 | Crew continued surveying in the northern part of the grid. The morning was rocky with sparse tree cover, but the afternoon had a lot of tall trees so time was taken to ensure good GNSS signal. |
| 15/08/2017 | Crew continued surveying today, working south through the grid to the southern-most lines then looping back to the north. Terrain was decent walking south, however had thick trees in the south running east to west. In the far east the crew was slowed by rocky hills covered in deadwood. Total deadwalk today of 5km morning and afternoon combined. |
| 16/08/2017 | Crew continued surveying in the northern part of the grid. Most of the day was spent amoung tall trees 15m in height. Crew waited at each point a little longer than usual. Far Eastern section was more open with some outcrop. |
| 17/08/2017 | Crew continued surveying today, working south through the grid to the southern-most lines then looping back to the north with a deadwalk back to the car. Terrain in far southeast was slow going with outcrop and deadwood. |
| 18/08/2017 | Crew performed L shape again today. Tough terrain slowed crew as there were rocky outcrops with deadwood. 2.7km deadwalk on way home. Arrived back at base to see the lights acting strange and took a while for GPS to shut down via handheld. |
| 19/08/2017 | Crew again did the L shape loop to the bottom and all the way back to the top. Terrain was a little easier today giving us enough time to minimise deadwalks by collecting everything we past. Base GPS acting strange again with recording light not blinking at consistant rate. |
| 20/08/2017 | Today crew did the usual L shape loop. At the far end of the line tackled more of the rocky outcrops on the above lines before looping back. Tilt Test and toolbox performed once arrived back at camp. |
| 21/08/2017 | Today crew were able to bring up the bottom lines a lot more as the loops are getting shorter. At times there were some outcrops that took some time to overcome. Mostly forest on flatter ground saw production improve. |
| 22/08/2017 | Crew continued surveying central east section of grid brnging lines upwards. Terrain was mostly rocky today. |
| 23/08/2017 | Crew surveyed the eastern section getting further north of the grid. Terrain was mostly flat with some a few stations on the extremities on outcrops which made production more consistent. |
| 24/08/2017 | Crew finished all stations in the eastern side of the grid then made their way to the western section and worked their way down until time to finish. |
| 25/08/2017 | Crew collected all remaining stations. Received message about repeating stations from the 19th so collected 10 more stations from that day. Turned off base as normal however discovered back at camp office that some data was corrupted. |
| 26/08/2017 | Crew collected stations from the 19th of August. Came back to base to find it had stopped recording. Lost some acquired stations from the afternoon. |
| 27/08/2017 | Crew swapped the base and the rover so the buggy rover was on field with the crew and could be monitored. Looked at the flash recording at each station before taking a read. Had to shut down multiple times during the day as the rover would stop recording. All stations reacquired. |
| 28/08/2017 | Crew mobilise to Darwin and fly back to Perth. |

| FIELD | MEAN | SD | MINIMUM | MAXIMUM |
| --- | --- | --- | --- | --- |
| DIFFEASTM | -0.024 | 0.218 | -1.178 | 0.410 |
| DIFFNORTHM | 0.011 | 0.221 | -0.543 | 0.840 |
| DIFFHTM | 0.004 | 0.024 | -0.033 | 0.048 |
| DIFFOBSGMGAL | -0.001 | 0.022 | -0.046 | 0.047 |
| DIFFOBSGGU | -0.006 | 0.224 | -0.460 | 0.470 |